## Charts
As we transitioned from Sprint 3 to Sprint 4; the
team focused on clearing all severe/functional defects.
The net was an increase in the number of
defects with a reduction in severity.

## Data
| Story Points |  |  | Planned | Actual | Techincal
Sprint | Planned | Completed | Sprint | Velocity | Velocity | Debit
0 | 17 | 13 | 0 | 0 | 0 | 0
1 | 56 | 16 | 1 | 3.2941 | 1.2308 | 3
2 | 74 | 60 | 2 | 1.3214 | 3.75 | 15
3 | 34 | 19 | 3 | 0.45946 | 0.31667 | 13
4 | 9 | 9 | 4 | 0.26471 | 0.47368 | 20