## JIRA_SelectColumns
Issue key | Issue Type | Summary | Status | Description | Sprint | Created | Labels
PQVP-2 | Story | As a developer, I want to modify the front-end application to access the appropriate Dropwizard container for the environment | Done | *Acceptance Criteria* * The angular application accesses the correct Dropwizard container based on whether it's running in development (local mode), development (server mode), Test, or Production. | ADPQ Sprint 0 | 2017-01-31 22:34 | Development
PQVP-3 | Story | As a Developer, I want to update code to access environment-specific configuration information, so the application will point to the correct database for the environment | Done | *Acceptance Criteria* * Application code identifies database end point based on environment-specific configuration information. | ADPQ Sprint 0 | 2017-01-31 22:27 | Development
PQVP-4 | Story | As a DevOps engineer, I want to modify deployment scripts to support environment-specific database connections | Done | *Acceptance Criteria* * Deployment scripts perform all necessary steps to ensure that the application accesses the correct database. | ADPQ Sprint 0 | 2017-01-31 22:29 | DevOps
PQVP-5 | Story | As a Developer, I want to understand our code management strategy so I can implement our QA steps | Done | *Acceptance criteria* * Source code management approach document reflects current approach * Code strategy has been communicated * Developers understand code review procedures and objectives * Developers understand how to confirm their code check-in won't introduce regression bugs * Operational instructions for how to conduct peer reviews * Source code management approach document is in Confluence | PQVP Sprint 2 | 2017-01-31 21:53 | Development
PQVP-6 | Story | As a DevOps engineer, I want to confirm whether unit tests succeed or fail as appropriate so we don't deploy bad builds | Done | *Acceptance Criteria* * Dev Ops team has run Angular unit tests that should pass, and they passed * Dev Ops team has run Angular unit tests that should fail, and they failed * Dev Ops team has run Java unit tests that should pass, and they passed * Dev Ops team has run Java unit tests that should fail, and they failed | ADPQ Sprint 0 | 2017-01-31 21:58 | DevOps
PQVP-7 | Story | As a DevOps engineer, I want to install Maven and Selenium so we can implement automated functional testing | Done | *Acceptance Criteria* * Maven and Selenium are installed in our test environment | ADPQ Sprint 0 | 2017-01-31 22:20 | DevOps
PQVP-8 | Story | As a functional tester, I want to confirm that automated functional tests accurately report success or failure so we can implement our test strategy | Done | *Acceptance Criteria* * Selenium tests accurately report success or failure when they run in the Test environment. | PQVP Sprint 1 | 2017-01-31 22:24 | Test
PQVP-10 | Story | As a UX dev I need to revisit persona interview candidates for updated information | Done | *Acceptance Criteria*: * schedule update interviews with as many existing persona candidates as possible * determine where the gaps are in the personas we have not yet captured (birth parent, foster parent, etc.) * schedule interviews with individuals to cover the persona gaps | ADPQ Sprint 0 | 2017-01-30 17:26 | UI/UX
PQVP-11 | Story | As a UX dev I need to update all my template files to match the requirements for the PoC | Done | *Acceptance Criteria*: * based on the RFI that comes in, I need to go thru each of my template files and get them updated accordingly ** this includes colors, fonts, names, etc. so that they can be a part of the unified PoC document submission packet | PQVP Sprint 2 | 2017-01-30 17:34 | UI/UX
PQVP-12 | Story | As a UX dev I need to construct the login and profile UI flows the dev team will build from | Done | *Acceptance Criteria*: * need to construct UI flow diagrams to hand off to the dev team so that they know what the general flow of application feature set will be ** this includes all error handling and failure states as well ** login screen? ** profile screen ** | PQVP Sprint 1 | 2017-01-30 17:38 | stretch, UI/UX
PQVP-13 | Story | As a UX dev I need to construct login and profile wireframes/wireflows for the dev team to build from | Done | *Acceptance Criteria*: * need to construct the basic set of UI wireframes or wireflows that will illustrate to the dev team the general layout for the UI system for this feature * 2nd set of wires required to show responsive layout * if time permits construct a click-thru/interactive wireframe to demonstrate how a user will interact with this UI and how we expect the UI to react to user input (animations, error, success states) ** login screen ** profile screen | PQVP Sprint 1 | 2017-01-30 17:41 | stretch, UI/UX
PQVP-14 | Story | Review Team Agreements | Done | *Acceptance Criteria* * Team has discussed revised agreements * Team agreements have been updated per team discussions | ADPQ Sprint 0 | 2017-01-13 21:13 | Other
PQVP-15 | Story | Determine what metrics / burndown measures to capture and how | Done | AC: Able to produce metrics and charts. | ADPQ Sprint 0 | 2017-01-26 17:31 | Other
PQVP-16 | Story | As a Security Engineer, I want to research and select an automated security tool so that I can execute vulnerability scans. | Done | *Acceptance Criteria* * Tool Identified * Pros and Cons of tool identified * Costs identified * Configurability of tool understood Factors are simplicity of integration and ability to automate. | ADPQ Sprint 0 | 2017-01-17 19:35 | Security
PQVP-17 | Story | As a Technical Architect I wanto to create a developer onboarding list so we can have standard dev environments for the development team | Done | *Acceptance Criteria* * List of onboarding tasks * Peer review and approval by Development Team | PQVP Sprint 2 | 2017-02-02 11:15 | Developers
PQVP-18 | Story | As a Security Engineer, I want to ensure users can access our Privacy Policy so that we address Privacy Act considerations | Ready | Address in this policy: * Why information is collected * How it is stored, used, and shared * How confidentiality of the information is protected in storage and in transit * How long it is retained * Whether and how the user can correct, delete, or remove this information * Whether and how the user will be notified in case of a breach * Who to contact for more information * Who to contact if there is a security issue Consider starting with a State-approved Privacy Policy page (e.g., http://www.coveredca.com/privacy/) and tailoring for the this project |  | 2017-02-02 13:03 | Security
PQVP-19 | Story | As a Security Engineer, I want to ensure that the application is subjected to a penetration test prior to deploying it into production so that we can identify and remediate vulnerabilities | Ready | This refers to Dynamic Application Security Testing (DAST) -- testing an application while it is running to identify potential vulnerabilities. Recommended tools include OWASP ZAP or the Burp Suite. Manually invoking the tool is adequate for this use case. Remediation (which typically require code changes) should be performed for vulnerabilities rated as high. Note that DAST should ideally be performed in addition to Static Application Security Testing (SAST) -- scanning source code for quality or security issues. |  | 2017-02-02 13:16 | Security
PQVP-20 | Story | As a technical architect, I want to optimize the architecture to deliver of static content quickly, so pages render quickly. | Ready | *Acceptance Criteria* * Architecture design has been updated to deliver static content quickly. * Design documentation reflects the change. * Architecture has been updated to implement the design changes. |  | 2017-02-02 13:55 | TechArch
PQVP-22 | Story | As a DevOps engineer, I want to research the best way to schedule deployments to Test so we can implement our CD approach | Done | *Acceptance Criteria* * We understand how best to schedule deployments to Test. We believe cron will work but if Jenkins has a scheduler, that might be a better solution. | PQVP Sprint 1 | 2017-01-31 22:16 | DevOps
PQVP-23 | Story | As a DevOps engineer, I want to write deployment scripts that support scheduling, so we can implement our CD approach | Done | *Acceptance Criteria* * Deployment scripts support scheduling * Verify IP addresses are updated automatically | PQVP Sprint 1 | 2017-01-31 22:18 | DevOps
PQVP-24 | Story | As a DevOps engineer, I want to implement scheduled deployments to Test, so we can implement our CD approach | Done | *Acceptance Criteria* * Builds are deployed to the Test environment on a nightly basis. * Ad hoc deployments continue to be available in addition to scheduled deployments. | PQVP Sprint 1 | 2017-01-31 22:18 | DevOps
PQVP-25 | Story | As a DevOps engineer, I want to integrate Maven and Selenium into our CD process so functional tests run automatically upon deployment to Test | Done | *Acceptance Criteria* * Maven and Selenium are integrated into the build process. * Automated functional tests run automatically upon deployment to Test. | PQVP Sprint 2 | 2017-01-31 22:22 | DevOps
PQVP-26 | Story | As a technical architect, I want to install New Relic so that we can monitor deployed environments. | Done | *Acceptance Criteria* * New Relic has been installed in our environments. | PQVP Sprint 1 | 2017-01-31 22:31 | TechArch
PQVP-27 | Story | As a technical architect, I want to configure New Relic to monitor deployed environments | Done | *Acceptance Criteria* * Dev Ops team has tested monitoring in Test and Production environments. | PQVP Sprint 3 | 2017-01-31 22:32 | TechArch
PQVP-28 | Story | As a UI/UX dev I need to coordinate with the dev team to get the style sheet correctly implemented | Done | *Acceptance Criteria*: * work with the client developers to get the style sheet nailed down and properly implemented to reflect the design aesthetic we plan to utilize in the final PoC * determine which set of UI components we want to use based on the prescribed function we determine is necessary to fulfill the RFI requirements * get stylesheet assets uploaded to Confluence | PQVP Sprint 4 | 2017-01-30 17:36 | UI/UX
PQVP-29 | Story | As a UX dev I need to conduct final persona interviews | Done | *Acceptance Criteria*: * conduct final persona interviews with existing candidates and with those we need to fill the personality type gaps (i.e. California resident, administrative user, etc) * aggregate data so that it can be translated into Persona document for PoC submission | PQVP Sprint 2 | 2017-01-30 17:29 | UI/UX
PQVP-30 | Story | As a UX dev I need to build final Persona documentation | Done | *Acceptance Criteria*: * use the aggregated data from the Persona interviews to modify and complete the existing Persona template and get it into a finalized format for PoC submission | PQVP Sprint 2 | 2017-01-30 17:32 | UI/UX
PQVP-31 | Story | As a UX dev I need to identify usabilty test participants | Done | *Acceptance Criteria*: * need to contact existing participants and make sure they have completed their Pre-study questionnaires and get them scheduled for future usability tests * also need to provide user with post-study exit questionnaires | PQVP Sprint 2 | 2017-01-30 18:10 | UI/UX
PQVP-32 | Story | As a UX dev I need to construct the admin notification publishing UI flows the dev team will build from | Done | *Acceptance Criteria*: * need to construct UI flow diagrams to hand off to the dev team so that they know what the general flow of application feature set will be ** this includes all error handling and failure states as well | PQVP Sprint 1 | 2017-01-30 18:45 | UI/UX
PQVP-33 | Story | As a UX dev I need to construct admin notification publish wireframes/wireflows for the dev team to build from | Done | *Acceptance Criteria*: * need to construct the basic set of UI wireframes or wireflows that will illustrate to the dev team the general layout for the UI system for this feature * 2nd set of wires required to show responsive layout * if time permits construct a click-thru/interactive wireframe to demonstrate how a user will interact with this UI and how we expect the UI to react to user input (animations, error, success states) | PQVP Sprint 1 | 2017-01-30 17:42 | UI/UX
PQVP-35 | Story | As a UX dev I need to construct the admin track, analyze and visualize UI flows the dev team will build from | Done | *Acceptance Criteria*: * need to construct UI flow diagrams to hand off to the dev team so that they know what the general flow of application feature set will be ** this includes all error handling and failure states as well | PQVP Sprint 1 | 2017-01-30 18:46 | UI/UX
PQVP-36 | Story | As a UX dev I need to construct admin track, analyze, and visualize wireframes/wireflows for the dev team to build from | Done | *Acceptance Criteria*: * need to construct the basic set of UI wireframes or wireflows that will illustrate to the dev team the general layout for the UI system for this feature * 2nd set of wires required to show responsive layout * if time permits construct a click-thru/interactive wireframe to demonstrate how a user will interact with this UI and how we expect the UI to react to user input (animations, error, success states) | PQVP Sprint 2 | 2017-01-30 17:42 | UI/UX
PQVP-37 | Story | As a UX dev I need to complete a usability test plan and supporting docs | Done | *Acceptance Criteria*: * design and document our usability test plan based on the RFI requirements * create the facilitator scripts to support usability testing * create the usability activity scenario plan to support the facilitator scripts and test plan * make sure to cross check documents (test plan and facilitator scripts primarily) to make sure they meet the 6th grade reading level requirement | PQVP Sprint 2 | 2017-01-30 18:35 | UI/UX
PQVP-38 | Story | As a UX dev I need to conduct usability test for feature set 1 | Done | *Acceptance Criteria*: * conduct usability tests with pre-screened participants (must have their pre-study questionnaires completed) * need to have a publicly accessible URL to conduct the web based tests from * gather and aggregate data to be used for making recommendations and the final usability report * feature set one to include login and profile creation screens (ad-hoc notifications will need to be tested in a future sprint as they are not yet ready to be tested) * | PQVP Sprint 2 | 2017-01-30 18:38 | UI/UX
PQVP-39 | Story | As a UX dev I need to conduct usability tests for feature set 2 | Done | Feature set 2 refers to the admin pages. *Acceptance Criteria*: * conduct usability tests with pre-screened participants (must have their pre-study questionnaires completed) * need to have a publicly accessible URL to conduct the web based tests from * gather and aggregate data to be used for making recommendations and the final usability report | PQVP Sprint 3 | 2017-01-30 18:38 | UI/UX
PQVP-40 | Story | As a UX dev I need to make iteration recommendations based on usability test results - Pt 1 | Done | *Acceptance Criteria*: * review usability test results and make iteration recommendations for future development cycles (write user stories) | PQVP Sprint 2 | 2017-01-30 18:49 | UI/UX
PQVP-42 | Story | As a UX dev I need to make iteration recommendations based on usability test results - Pt 2 | Done | *Acceptance Criteria*: * review usability test results and make iteration recommendations for future development cycles (write user stories) | PQVP Sprint 3 | 2017-01-30 18:49 | sprint3, UI/UX
PQVP-43 | Story | As a UX dev I need to create a finalized Usability Test Results Report | Done | *Acceptance Criteria*: * take all data generated by the 3 usability test scenarios and aggregate them into a single Usability Test Results Report * this report should use the InD template created and should be output in the form of a PDF for ease of interactive consumption | PQVP Sprint 4 | 2017-01-30 18:40 | sprint4, Sprint4Planning, UI/UX
PQVP-45 | Story | As a DevOps engineer, I want to install and configure Sonarqube, and integrate it with our CI tools so we can confirm that our code meets security standards. | Ready | *Acceptance Criteria* * Sonarqube is installed in our environment * Sonarqube tests run when developers check in code * Sonarqube tests run at the time of a build * DevOps team has defined how results will be interpreted, including how false positives will be distinguished from actual problems * DevOps team has defined how results will be reported *Notes* See the document linked to ADPQ-16 for installation/configuration recommendations. Original notes on this topic said: Implementation approach should be as simple as possible for purposes of POC. A larger project or one with different scalability requirements might require a more complex implementation such as containerizing the Sonarqube server, putting the Sonarqube database on its own server, or package management. |  | 2017-01-31 22:14 | DevOps, Security
PQVP-46 | Story | As a DevOps engineer, I want to implement automated accessibility testing to streamline our process | Ready | *Acceptance Criteria* * Accessibility tests run automatically when developer checks in code * Accessibility tests run automatically at the time of a build |  | 2017-01-31 22:37 | DevOps
PQVP-47 | Story | As a technical architect, I want to implement realtime resource allocation based on user demand so our Production environment is better able to handle fluctuations in demand | Ready | *Acceptance Criteria* * Azure resources are scaled up or down based on demand * Azure resources do not scale up beyond predetermined maximums |  | 2017-01-31 22:39 | DevOps
PQVP-48 | Story | As a technical architect, I want to implement API-based resource provisioning so I can better control resource usage | Ready | *Acceptance criteria* * Resources can be provisioned via API |  | 2017-01-31 22:41 | TechArch
PQVP-49 | Story | As a technical architect, I want to implement load/performance testing so I can better assist developers in tuning the application | Ready | *Acceptance criteria* * Load/performance test approach is designed and implemented |  | 2017-01-31 22:42 | TechArch
PQVP-50 | Story | As a technical architect, I want to configure New Relic to send automated alerts so I can better monitor resource usage | Ready | *Acceptance Criteria* * New Relic sends automated alerts based on predefined thresholds. |  | 2017-01-31 22:43 | TechArch
PQVP-51 | Story | As a technical architect, I want to implement website analytics so I can monitor and publish usage information | Ready | *Acceptance Criteria* * Website analytics are implemented * Metrics are published internally * Strategy defined for publishing metrics externally |  | 2017-01-31 22:46 | TechArch
PQVP-52 | Story | As a developer, I want to implement a feedback mechanism for users to report bugs and suggest features, so that user concerns can be addressed efficiently | Ready | *Acceptance Criteria* * Application supports user reports of defects. * Application supports user requests for new features. |  | 2017-01-31 22:48 | Developers
PQVP-53 | Story | As a developer, I want to migrate to an open version of Jira, so my user community is fully aware of reported issues and their status | Ready | *Acceptance Criteria* * Project has migrated to an open instance of Jira * Users have access to Jira stories and bugs *Notes* * Need to determine whether project issues/bugs are available to the general public, or only to application users |  | 2017-01-31 22:52 | Developers
PQVP-54 | Story | As a user whose primary language is Spanish, I want to interact with the application in Spanish to minimize miscommunications | Ready | *Acceptance Criteria* * Sample login application allows selection of Spanish or English * Static text content in the application appears in the selected language * Framework is established for future features to appear in the selected language. *Notes* * While this story specifically references Spanish, we should implement in a way that supports expansion to other languages |  | 2017-01-31 23:17
PQVP-55 | Story | As a UX dev I want to be construct flow templates to be better prepared for upcoming feature designs | Done | *Acceptance Criteria*: * construct templates to build from that will help springboard feature 1 development | ADPQ Sprint 0 | 2017-02-03 10:30 | UI/UX
PQVP-58 | Epic | User Login, Landing Page, and Profile Management | Ready | As a user, I want to log into the application and manage my user profile so the system will be able to send me notifications effectively. |  | 2017-02-07 20:48
PQVP-59 | Epic | Receiving Notifications | Ready | As a user, I want to receive notifications based on my contact preferences, so I'm aware of events that might affect me. This includes emergency and non-emergency notifications, sent via email, SMS, and/or push notifications. |  | 2017-02-07 20:49
PQVP-60 | Epic | Geo-location Notifications | Ready | As a user, I want to receive notifications based on my location so I can be aware of events near me. |  | 2017-02-07 21:11
PQVP-61 | Epic | Notification Links | Ready | As a user, I want to be able to follow a link in notifications to find more information about an event |  | 2017-02-07 21:13
PQVP-62 | Epic | Admin: Publish Notifications | Ready | As a administrative user, I want to be able to publish notifications based on location. This includes emergency and non-emergency notifications. |  | 2017-02-07 21:15
PQVP-63 | Epic | Admin: Track, Analyze, Visualize | Ready | As a administrative user, I want to be able to track, analyze, and visualize information about notifications sent. |  | 2017-02-07 21:18
PQVP-64 | Epic | User: Service Based Notifications | Ready | As a user, I want to be notified of emergency events related to fire, river, weather, earthquake, tsunami, and DOI GEMS emergency information. |  | 2017-02-07 21:21
PQVP-65 | Epic | User: Notify based on Geo-location | Ready | As a user, I want my geolocation to be captured when I use the application so I can be notified of events near me. |  | 2017-02-07 21:23
PQVP-66 | Epic | Database Reset | Ready | As a Delivery Manager, I want to ensure that the database has been reset to an empty state before the first production release. |  | 2017-02-07 21:26
PQVP-67 | Story | As a user, I want to receive notifications by email if specified in my contact preferences, so I'm aware of emergency and non-emergency events that might affect me. | Done | *Acceptance Criteria* * Notifications are sent via email if my contact preferences specify that I want to receive notifications via email. * No notifications are sent via email if my contact preferences specify that I do not want to receive notifications via email. *Notes* The content of the notification should be as indicated in https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/PQVP%20Notification%20Text.docx. | PQVP Sprint 2 | 2017-02-07 21:38 | Development
PQVP-68 | Story | As a user, I want to receive notifications by text message if specified in my contact preferences, so I'm aware of emergency and non-emergency events that might affect me. | Done | *Acceptance Criteria* * Notifications are sent via text message if my contact preferences specify that I want to receive notifications via text message. * No notifications are sent via text message if my contact preferences specify that I do not want to receive notifications via text message. *Notes* The content of the notification should be as indicated in https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/PQVP%20Notification%20Text.docx. | PQVP Sprint 2 | 2017-02-07 21:38 | Development
PQVP-69 | Story | As a user, I want to receive notifications by push notification if specified in my contact preferences, so I'm aware of emergency and non-emergency events that might affect me. | In Progress | This story is to implement push notifications to a user who has the Chrome browser open on Android. Notification is outside the web app. Confirm if Safari/IOS and IE are viable w/o plugins. *Acceptance Criteria* * Notifications are sent via push notification if my contact preferences specify that I want to receive notifications via push notification. * No notifications are sent via push notification if my contact preferences specify that I do not want to receive notifications via push notification. *Notes* The content of the notification should be as indicated in https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/PQVP%20Notification%20Text.docx. | PQVP Sprint 3 | 2017-02-07 21:39 | Developers, Mobile
PQVP-70 | Story | As a developer, I want to automate polling the Active Fire Boundaries (USGS GeoMAC) service so the application can send out timely emergency notifications. | Done | *Acceptance Criteria* * The application polls the https://wildfire.cr.usgs.gov/ArcGIS/rest/services/geomac_dyn/MapServer service periodically, for instance, every 15 minutes. * The application polls the https://wildfire.cr.usgs.gov/ArcGIS/rest/services/geomac_perims/MapServer service periodically periodically, for instance, every 15 minutes. * The application polls the https://wildfire.cr.usgs.gov/ArcGIS/rest/services/geomac_fires/MapServer service periodically periodically, for instance, every 15 minutes. * If, in polling the above services, an event is found, the application captures the event information. *Note* Be aware that the polling frequency requirement may change. | PQVP Sprint 2 | 2017-02-07 22:08 | Development
PQVP-71 | Story | As a developer, I want to automate polling the River Gauge - Current and Forecast (NOAA) service so the application can send out timely emergency notifications. | Done | *Acceptance Criteria* * The application polls the https://idpgis.ncep.noaa.gov/arcgis/rest/services/NWS_Observations/ahps_riv_gauges/MapServer service periodically, for instance, every 15 minutes. * The application polls the https://idpgis.ncep.noaa.gov/arcgis/rest/services/NWS_Forecasts_Guidance_Warnings/sig_riv_fld_outlk/MapServer service periodically, for instance, every 15 minutes. * The application polls the https://idpgis.ncep.noaa.gov/arcgis/rest/services/NWS_Forecasts_Guidance_Warnings/wpc_qpf/MapServer service periodically, for instance, every 15 minutes. * If, in polling the above services, an event is found, the application captures the event information. *Note* Be aware that the polling frequency requirement may change. | PQVP Sprint 2 | 2017-02-07 22:29 | Development
PQVP-72 | Story | As a developer, I want to automate polling the Weather Hazards (NOAA) service so the application can send out timely emergency notifications. | Done | *Acceptance Criteria* * The application polls the https://idpgis.ncep.noaa.gov/arcgis/rest/services/NWS_Climate_Outlooks/cpc_weather_hazards/MapServer service periodically, for instance, every 15 minutes. * The application polls the https://idpgis.ncep.noaa.gov/arcgis/rest/services/NWS_Forecasts_Guidance_Warnings/watch_warn_adv/MapServer service periodically, for instance, every 15 minutes. * If, in polling the above services, an event is found, the application captures the event information. *Note* Be aware that the polling frequency requirement may change. | PQVP Sprint 2 | 2017-02-07 22:31 | Development
PQVP-73 | Story | As a developer, I want to automate polling the Earthquakes (USGS) service so the application can send out timely emergency notifications. | Ready | *Acceptance Criteria* * The application polls the http://sampleserver3.arcgisonline.com/arcgis/rest/services/Earthquakes/EarthquakesFromLastSevenDays/MapServer service periodically, for instance, every 15 minutes. * If, in polling the above services, an event is found, the application captures the event information. *Note* Be aware that the polling frequency requirement may change. | PQVP Sprint 1 | 2017-02-07 22:32 | Developers
PQVP-74 | Story | As a developer, I want to automate polling the Tsunami (NOAA) service so the application can send out timely emergency notifications. | Ready | *Acceptance Criteria* * The application polls the https://maps.ngdc.noaa.gov/arcgis/rest/services/web_mercator/hazards/MapServer service periodically, for instance, every 15 minutes. * If, in polling the above services, an event is found, the application captures the event information. *Note* Be aware that the polling frequency requirement may change. | PQVP Sprint 1 | 2017-02-07 22:33 | Developers
PQVP-75 | Story | As a developer, I want to automate polling the Interior Geospatial Emergency Management System (DOI IGEMS) service so the application can send out timely emergency notifications. | Ready | *Acceptance Criteria* * The application polls the https://igems.doi.gov/arcgis/rest/services/igems_haz/MapServer service periodically, for instance, every 15 minutes. * The application polls the https://igems.doi.gov/arcgis/rest/services/igems_info/MapServer service periodically, for instance, every 15 minutes. * If, in polling the above services, an event is found, the application captures the event information. *Note* Be aware that the polling frequency requirement may change. | PQVP Sprint 1 | 2017-02-07 22:34 | Developers
PQVP-76 | Story | As a user, I want to create a user profile so I can register for notifications. | Done | *Acceptance Criteria* * User is able to enter ZIP code information. * User is able to specify their preferred notification method(s) (notification by email and/or SMS and/or push notifications). * User is able to enter their domestic mobile phone number. * User is able to enter their email address. * Application does not allow saving unless at least one of the notification methods is selected. * Application does not allow saving if phone number is not ten digits. * Application does not allow saving if email address is in an invalid format. * Application does not allow saving if notification by email is selected and email address is blank. * Application does not allow saving if notification by SMS and/or push notifications is selected and phone number is blank. * Application does not allow saving if the ZIP code is blank or is not exactly 5 digits. * If the user attempts to save and the data passes all validations, the data is persisted. * If the user cancels, no user profile is created. * Application meets the [UI General Acceptance Criteria¦https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/UI%20General%20Acceptance%20Criteria.docx] *Notes* There is no requirement to accept foreign address or phone number information. | PQVP Sprint 2 | 2017-02-07 22:52 | development, UI/UX
PQVP-77 | Story | As a user, I want to modify my user profile so I can update my registration preferences. | Done | *Acceptance Criteria* * User is able to modify their ZIP code. * User is able to modify their preferred notification method(s) (notification by email and/or SMS and/or push notifications). * User is able to modify their domestic mobile phone number. * User is able to modify their email address. * Application does not allow saving if phone number is not ten digits. * Application does not allow saving if email address is in an invalid format. * Application does not allow saving if notification by email is selected and email address is blank. * Application does not allow saving if notification by SMS and/or push notifications is selected and phone number is blank. * If no notification method is selected, the application informs the user that no further notifications will be received. * Application does not allow saving if the ZIP code is blank or is not exactly 5 digits. * If the user attempts to save and the data passes all validations, the data is persisted. * If the user cancels, no data is changed in the database. * Application meets the [UI General Acceptance Criteria¦https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/UI%20General%20Acceptance%20Criteria.docx] *Notes* * Application allows saving even if none of the notification methods is selected, to support "unsubscribing" from alerts. * There is no requirement to accept foreign address or phone number information. | PQVP Sprint 2 | 2017-02-07 22:56 | Development, UI/UX
PQVP-79 | Story | As a user, I want to be able to secure my account with a password so I can be confident that others are not viewing or changing my information. | Done | *Acceptance Criteria* * When creating a user profile, user must enter a password. * Password is not displayed or changeable on the "update user profile" page. * When the user saves a new user profile, the application encrypts the password before saving it. * When attempting to access an existing user profile, user must enter their password. If the password entered (after being encrypted) does not match the one on the user profile, the application does not allow the user access to the profile. * Application meets the [UI General Acceptance Criteria¦https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/UI%20General%20Acceptance%20Criteria.docx] | PQVP Sprint 2 | 2017-02-07 23:09 | Development, Security, UI/UX
PQVP-80 | Story | As a user, I want to be able to change my password so I can protect my information. | Done | *Acceptance Criteria* * When updating a user profile, user has the option of updating their password. The password must be entered twice. * When the user attempts to save after changing their password, the application does not allow saving if the two entered passwords do not match. * When the user updates their password and saves their user profile, the application encrypts the password before saving it. * Application meets the [UI General Acceptance Criteria¦https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/UI%20General%20Acceptance%20Criteria.docx] | PQVP Sprint 2 | 2017-02-07 23:09 | Development, Security, UI/UX
PQVP-81 | Story | As a user, I want to be able to recover my password if I forget it so I can continue to access the application. | Ready |  |  | 2017-02-07 23:13 | Developers, Security, UI/UX
PQVP-82 | Story | As a Security engineer, I want to secure traffic to our application using SSL. | Done | *Acceptance Criteria* * SSL certs have been procured and installed in the web serverâ€™s Docker container. * Application transmits data via https rather than http. | PQVP Sprint 3 | 2017-02-07 23:14 | Security
PQVP-89 | Story | As a DevOps engineer I need to ensure the DB is cleaned as part of deployment | Done | *Acceptance criteria* - After a production deployment: * No user information remains in the database other than the admin user and a sample user. * No notification information remains in the database except for notifications associated with the sample user. * No information about ad hoc events remains in the database. *Note* When deploying the application to the final POC deploy area we need to ensure the DB is scrubbed of data. To the extent we've collected events during our testing against our external data sources, those events should remain in the database to support analysis functions. | PQVP Sprint 4 | 2017-02-08 11:53 | Developers
PQVP-90 | Story | As a Product Owner, I want to confirm consistent naming and look & feel for the application so it appears professional and consistent. | Done | *Acceptance Criteria* * Name of application has been determined. * Domain name has been determined. * Domain name has been purchased. * Logo has been designed. * Styles and style guide have been defined, including icons and images. * Digital style guide has been updated to reflect the naming and look & feel * Updated digital style guide has been posted to Confluence. | PQVP Sprint 4 | 2017-02-08 13:50
PQVP-92 | Sub-task | Implement user profile back-end changes | Done | *Acceptance criteria* * Implement POST REST end-point for user profile registration. * Create the required database DDL to satisfy user registration. * Ensure the end-point is accessible and documented from Swagger. * Remove unrelated project files which were created during pre-poc exercises. * Integrate with Google Maps API for retrievining Longitude and Latitude by Zipcode when user registers. | PQVP Sprint 2 | 2017-02-09 11:31
PQVP-93 | Story | As an end user, I should have content presented to me in a way that is familiar and easy to understand | Done | *Acceptance Criteria*: * Application has been reviewed for language complexity. * Any user-facing content that is not at a 6th grade or lower reading level has been identified for remediation. |  | 2017-02-09 13:06 | UI/UX
PQVP-94 | Sub-task | Implement user profile front-end changes | Done |  | PQVP Sprint 2 | 2017-02-12 19:17
PQVP-95 | Story | As a developer, I want to automate polling additional data layers so the application can send out additional emergency notifications. | Ready | *Acceptance Criteria* * The application polls additional services and data layers periodically, for instance, every 15 minutes. * If, in polling the above services, an event is found, the application captures the event information and generates appropriate notifications. *Notes* * Additional detail to be added as this is moved into a sprint. The intent is that this story cover any remaining data layers we seek to automate within the POC, starting with the U.S. Volcanoes (1) layer of the https://igems.doi.gov/arcgis/rest/services/igems_haz/MapServer service. * Be aware that the polling frequency requirement may change. |  | 2017-02-13 02:41 | Developers
PQVP-96 | Story | As an administrative user, I want to publish ad hoc notifications so I can make subscribers aware of events that don't come from our automated data sources. | Done | - Non-admin user is not able to access the page - Admin user is able to select from a pre-defined list of event types: * Non-Emergency * Emergency - Admin user is able to enter between one and twenty ZIP codes to identify the location of the event. - | PQVP Sprint 2 | 2017-02-13 02:55 | Development
PQVP-97 | Story | As an administrative user, I want to track, analyze, and visualize notification data so I can identify proactively identify problems or trends. | Done | *Acceptance Criteria* * Non-admin user is not able to access the page * This page displays after an admin user logs in. * Admin user is able to view multiple events (at least the ten most recent). * Admin user is able to filter the events viewed by date and event type * For each event, admin user is able to view details including the event type, number of users notified, and the message that was sent. * Admin user is able to view a visual representation of event location. * Application meets the [UI General Acceptance Criteria¦https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/UI%20General%20Acceptance%20Criteria.docx] *Notes* * The team should take into account performance of the page in determining how many events to show at a time -- the page should be reasonably responsive. * Admin should also be able to "Search by Zip Code" - if no events found that match entered criteria, then the list should be empty, but should display a string stating the following: "No events found that match your criteria" | PQVP Sprint 2 | 2017-02-13 02:57 | Development
PQVP-98 | Story | As a user, I want to receive notifications via my chosen notification methods when my location is within 50 miles of an emergency or non-emergency event location. | Done | *Acceptance Criteria* * Automated and ad hoc events that occur within 50 miles of my location result in my being notified by my selected notification methods. * Automated and ad hoc events that occur more than 50 miles from my location do not result in my being notified. *Notes* * Be aware that the distance requirement may change to something other than 50 miles, or to a value the user can set. * For purposes of this story, the +*user's*+ location is a single point. If all we know is a ZIP code, that point would be the centroid of the ZIP code. If we have a more precise location (via more comprehensive data collection or geo-location), that location would be used instead. Future stories may refine this to treat a ZIP code as a region. * For purposes of this story, the +*event*+ location is a single point, which may be the centroid of a ZIP code for ad hoc notifications. * The content of the notification should be as indicated in https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/PQVP%20Notification%20Text.docx. | PQVP Sprint 2 | 2017-02-13 03:21
PQVP-100 | Story | As an administrative user, I want to select the area affected by an ad hoc event visually, so I can quickly select a large or small area. | Ready | *Acceptance Criteria* * On the publish notifications page, admin user can interact with a map to identify the geography covered by an ad hoc event. This replaces the ZIP code entry control. * Application does not allow saving if no geography is identified. * After data is saved, the application sends notifications to users based on proximity to the selected range. - Application meets the [UI General Acceptance Criteria¦https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/UI%20General%20Acceptance%20Criteria.docx] |  | 2017-02-13 10:54 | Developers, UI/UX
PQVP-101 | Story | As a technical architect, I want to optimize database performance by limiting the amount of data in our operational stores. | Ready | *Acceptance Criteria* * As events expire, move event data to a separate data store that supports analysis and reporting but does not impact operational performance. * "Expired event" is defined as an event that was last received more than 24 hours ago. |  | 2017-02-13 11:29 | TechArch
PQVP-102 | Story | As a user, I would like to see useful information after a successful login so the application provides more value than just showing me my profile. | Done | *Acceptance Criteria* - User landing page displays after any of the following events occurs: * Successful login * Saving profile * Canceling an update profile attempt - User is able to view a list of events they've been notified of (at least the ten most recent) - For each event, user is able to view the event type and the message that was sent. - User is able to view a visual representation of event location. - Application meets the [UI General Acceptance Criteria¦https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/UI%20General%20Acceptance%20Criteria.docx] *Notes* User is not able to view information about notifications that were sent to other users, including a count of users or notifications. | PQVP Sprint 2 | 2017-02-13 17:16 | Developers, UI/UX
PQVP-103 | Story | As a user, I want to be able to get more information about an event when I receive a notification. | Ready | *Acceptance Criteria* * Hyperlink in notification takes user directly to an event map page * The user is able to view the event type and the message that was sent * The user is able to view a visual representation of the event location. * The event map page displays whether the user is logged in or not, and does not prompt the user for a login. * Application meets the [UI General Acceptance Criteria¦https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/UI%20General%20Acceptance%20Criteria.docx] *Notes* * Some data sources provide a URL in their response data. It hasn't been decided yet whether we're going to provide that link in the notification, if available, rather than a link to our event map page. * Although the event map page does not require the user to be logged in, it may appear differently if the user is logged in. |  | 2017-02-13 17:25 | Developers, NotificationCriteria, UI/UX
PQVP-104 | Story | As a user, I want to receive notifications based on my last known location. | Done | *Acceptance Criteria* * When user logs in to application from a device that supports geo-location, the application captures their current location. * The application persists the location *Notes* The captured location is stored in addition to the ZIP code on the profile, so the user will receive notifications associated with their last known location as well as notifications associated with their residence ZIP code. | PQVP Sprint 2 | 2017-02-14 12:34 | Developers
PQVP-105 | Story | As an end user when I create or update my Profile, I want to receive a confirmation email | Ready | *Acceptance Criteria*: * design the look and feel of the confirmation email * once a user has created and saved new profile information, he/she should receive an email confirming his/her registration * when a user updates profile information he/she should also receive a confirmation email |  | 2017-02-15 12:01 | UI/UX
PQVP-106 | Sub-task | Implement API's for Admin ad-hoc notifications | Done |  | PQVP Sprint 2 | 2017-02-15 15:47
PQVP-107 | Sub-task | Implement front end | Done | This UI would be similar to end user with addition of filtering capability. | PQVP Sprint 2 | 2017-02-16 16:00 | UI/UX
PQVP-108 | Story | As a user, I want to enter my location down to the street level, so notifications will be more precisely targeted. | Done | *Acceptance Criteria* * User is able to enter a domestic address on the user profile page. * ZIP code is required, and must be exactly five digits. * When determining whether the location of an event is close to the entered address, the application compares the event location to the centroid of the ZIP code, if that's all that was entered. If a full address was entered, the application uses that specific address. | PQVP Sprint 3 | 2017-02-17 00:33 | Developers, UI/UX
PQVP-109 | Story | As a user, I want an easy way to unsubscribe from alerts. | Ready | *Acceptance Criteria* * Unsubscribe link appears on the user's landing page * When the user clicks the Unsubscribe link, the application disables all notification methods for the user. The user is not removed from the system or disabled from logging in. * If the user accesses their user profile page after unsubscribing, all notification methods are unchecked. * If the user attempts to save on the user profile page without selecting any of the notification method checkboxes, the application does not allow the save. [This is how the application already behaves on create -- this AC just implements identical behavior for modifying profiles.] |  | 2017-02-17 00:37 | Developers, UI/UX
PQVP-110 | Story | As a user, I want to be barred from creating multiple accounts with the same email address, to reduce the chance of confusion. | Done | *Acceptance Criteria* * If a user attempts to register with an email address that is already registered in the system, the application disallows them from saving their profile. * Error message should match the message documented in wireframes. *Notes* This story does not implement any "forgot my password" functionality. | PQVP Sprint 3 | 2017-02-17 00:40 | Developers, UI/UX
PQVP-111 | Story | As a user, I want the system to alert me if it doesn't understand the entered address, to protect me from miskeying my address. | Ready | *Acceptance Criteria* * If the application cannot associate a latitude and longitude to the entered address or ZIP code, it does not allow the user to save their profile. |  | 2017-02-17 00:42 | Developers, UI/UX
PQVP-112 | Story | As a technical architect, I want to update the database usernames and passwords before going live, so outside parties cannot access the Test or Production databases. | Done | *Acceptance Criteria* * The mysql username and password for the test and production environments are different from those that might be found in Github. *Notes* At some point, apparently we stored the test environment database user name and password in github. This story is just to keep those passwords from being discovered and used. | PQVP Sprint 4 | 2017-02-17 00:45 | TechArch
PQVP-113 | Task | Implement update profile functionality for the backend | Done |  | PQVP Sprint 4 | 2017-02-17 13:53 | Developers
PQVP-114 | Bug | Login - Incorrect Username Label on Login screen | Done | The Username field on the Login page displays as Email instead of Username. | PQVP Sprint 3 | 2017-02-17 14:06 | Developers
PQVP-116 | Bug | Login - Incorrect error message received for invalid username | Done | On the Login page, when trying to log in with a blank username, the user receives the message 'Email is required' instead of the expected value of 'You must enter a valid username'. | PQVP Sprint 3 | 2017-02-17 14:14 | Developers
PQVP-117 | Bug | Login - Incorrect error message received for invalid password | Done | On the Login page, when trying to log in with a blank password, the user receives the message 'Password is required' instead of the expected value of "You must enter a valid password. Passwords must contain at least 8 characters and 3 of the folloowing: one uppercase letter, one lowercase letter, one number and/or one special character " | PQVP Sprint 3 | 2017-02-17 14:15 | Developers
PQVP-118 | Bug | Login - Username should not be case sensitive | Done | The Login page is applying a case sensitivity check on the username field. The username is an email address. There should be no case sensitivity check on the username field. |  | 2017-02-17 14:17 | Developers
PQVP-119 | Bug | User Profile - Requires non-required fields | Done | The User Profile page is requiring me to enter non-required fields: First Name, Last Name, and Phone Number. Phone Number is only supposed to be required when Text Message, Push Notification or Allow notifications by Phone is selected. | PQVP Sprint 3 | 2017-02-18 16:03 | Developers
PQVP-120 | Bug | Received text msg for registration confirmation | Done | After successfully creating my User Profile, I received a text message confirming my registration. However, in my profile set up I had specified to receive notifications by email. I would not expect a text without authorization to do so. Per PO, user should not receive a text message confirmation. User should be take to Registration Confirmation page. | PQVP Sprint 3 | 2017-02-18 16:07 | Developers
PQVP-122 | Bug | User Profile - Received incorrect msg regarding improper email address when creating user profile | Ready | When creating my user profile, I entered an invalid / improper email address. Instead of receiving a "You must enter a valid email address" I received "A valid email address is required" |  | 2017-02-18 16:14 | Developers
PQVP-123 | Bug | User Profile - Not prompted to confirm cancellation of user registration | Ready | When clicking the cancel button on the User Profile page, I was redirected to the Login page instead of being prompted to confirm the cancellation. |  | 2017-02-18 16:23 | Developers
PQVP-124 | Bug | Session Mgmt - Logged in URL keeps me logged in when copied to new/same browser | Done | I logged in on IE11 and went to Landing Page. Copied URL. Opened Chrome Browser and pasted in URL. Was taken to the Landing Page without having to log in. Also, did the same but copied it into a new tab of the same browser. same behavior. | PQVP Sprint 3 | 2017-02-18 16:44 | Developers
PQVP-125 | Bug | Session Mgmt: Hitting back after logging out take user back into the application | Done | I logged into the application then clicked log out. After hitting the browser Back button, I was taken back to the Landing Page in the application instead of being prompted to log back in. | PQVP Sprint 3 | 2017-02-18 16:47 | Developers
PQVP-126 | Story | As a user, I want to be aware of any additional information about an event so I can have all information available. | Ready | *Acceptance Criteria* * On the landing page, application provides a link for the user to any URL passed back by the service. * If user clicks that link, the application displays the target URL in a new browser tab. *Notes* * This story provides to end users the same functionality that PQVP-127 provides to Admin users. * Some sources provide no link (Hurricane is the only one of our initial 7 that falls into this category). In that case, this functionality does not apply. * Other sources (like fire) only provide a general link, not one specific to the reported event. For purposes of this story, we won't differentiate these -- if any URL is provided, we'll make it available. |  | 2017-02-18 19:00
PQVP-127 | Story | As a Administrative user, I want to be aware of any additional information about an event so I can have all information available. | Ready | *Acceptance Criteria* * On the landing page, application provides a link for the user to any URL passed back by the service. * If user clicks that link, the application displays the target URL in a new browser tab. *Notes* * This story provides to Admin users the same functionality that PQVP-126 provides to end users. * Some sources provide no link (Hurricane is the only one of our initial 7 that falls into this category). In that case, this functionality does not apply. * Other sources (like fire) only provide a general link, not one specific to the reported event. For purposes of this story, we won't differentiate these -- if any URL is provided, we'll make it available. |  | 2017-02-18 19:03 | Developers, UI/UX
PQVP-128 | Sub-task | back end changes | Done | implement api/DAO/Model changes related to displaying generated notifications | PQVP Sprint 2 | 2017-02-19 10:34
PQVP-129 | Bug | User Profile- Change phone number to one input field | Done | To follow US Design Standards and make validation easier, change phone number on the User Profile from three input fields to one input field. | PQVP Sprint 3 | 2017-02-19 14:52 | Developers
PQVP-130 | Bug | Login Page- Missing 'Please Login or Register' header | Done | Login Page- Missing 'Please Login or Register' header shown on the wireframe (SystemWireflow_v2_021717.pdf) | PQVP Sprint 3 | 2017-02-19 19:06 | Developers
PQVP-131 | Bug | Per wireframes, User Profile header should say 'Your Information' | Done | Per wireframes, User Profile header should say 'Your Information'. | PQVP Sprint 3 | 2017-02-20 11:56 | Developers
PQVP-132 | Story | As an end user, I would like to have a brief explanation of what I should expect by registering a profile | Done | *Acceptance Criteria* * The login page provides the following information: "MyCAlerts.com is an alert service for California residents which monitors emergency events, such as fires, floods, and weather events. We also inform registered users of emergency and non-emergency events near them, via email, text message, or push notification. Register here to sign up for alerts! Note that MyCAlerts is in its infancy, and hasn't yet implemented all emergency alerts. We will inform our users as we add more event types." *Notes* This is an improvement recommendation based on usability testing conducted with the end user persona participants. Generally the system was perceived as extremely easy to use, but the one common thread was the inclusion of a short blurb that explained, briefly, what a user should expect by giving us their personal information and registering a profile. |  | 2017-02-20 12:02 | improvement, UI/UX, usability
PQVP-134 | Bug | Page scrolling scrolls entire page include header | Done | When using pages like Create New User or Modify User, when using the scroll bar on the right side, the enter page is scrolling, not just the form itself. | PQVP Sprint 3 | 2017-02-20 12:40 | Developers
PQVP-135 | Bug | User Profile - Tabbing field to field does not cause page to scroll to active field | Done | The Create New User profile or Modifying Profile page, as the user tabs from field to field, the form does not move with the active field. So eventually as you tab, you are forced to use the scroll bar to see which field is currently active. | PQVP Sprint 3 | 2017-02-20 12:42 | Developers
PQVP-136 | Bug | Unable to create new user - ConnectionPoolTimeoutException | Done | When trying to create a new user, I receive the following error message: An Unknown exception has occured. Type: <javax.ws.rs.ProcessingException>. Message: <org.apache.http.conn.ConnectionPoolTimeoutException: Timeout waiting for connection from pool> | PQVP Sprint 3 | 2017-02-20 12:59 | Developers
PQVP-137 | Bug | User profile- Inline error message missing for duplicate email address | Done | When I was creating a new user profile, I received the server error: "Duplicate entry for key <email>" when I tried registering with a previously registered email address. I should have received an inline error message that says "This Username is already registered'. |  | 2017-02-20 13:23 | Developers
PQVP-138 | Bug | User Profile - Hitting Go/Return on incomplete Create User Profile screen incorrectly takes user to Login screen | Done | As a user on an Android phone, I was filling out the Create New User form. I filled in the First Name, Last Name, Email address, and Password then clicked Go. I was taken back to the Login Page. Would have expect it to attempt a Save and report errors about the missing required fields. In non-mobile, clicking Return is activating Cancel instead of Save. Likewise, hitting Cancel from the Manage Profile page also take user back to the Login page instead of the Landing Page. | PQVP Sprint 3 | 2017-02-20 14:06 | Developers
PQVP-139 | Story | As a UX developer, I need to perform final validation that the application is 508 and WCAG 2.0 compliant. | Done | *Acceptance Criteria* * Team has run compliance test tool on the application. * Team has generated a list of potential accessibility issues. | PQVP Sprint 4 | 2017-02-20 15:38 | UI/UX
PQVP-140 | Story | As a Product Owner, I want to ensure that the application URL is pointing correctly to the application so users can access it easily. | Done | *Acceptance Criteria* * Navigating to mycalerts.com brings up the production environment. * Application front-end communicates correctly with back-end. | PQVP Sprint 3 | 2017-02-20 15:40 | TechArch
PQVP-141 | Story | As a Technical Architect, I want to install and configure MYSQL on the production database server in order to stand up the production database. | Done | *Acceptance Criteria* * Database instance has been created and configured in Production. * Production application runs without connection pool errors. | PQVP Sprint 2 | 2017-02-20 15:46 | TechArch
PQVP-143 | Story | As a Technical Architect, I want to install docker on production web and app servers in order for the application to deploy and run correctly. | Done | *Acceptance Criteria* * Production deployments run according to our DevOps/change control plan. | PQVP Sprint 2 | 2017-02-20 15:51 | TechArch
PQVP-144 | Story | As a developer, I want to insert New Relic code so monitoring will work correctly in production. | Done | *Acceptance Criteria* * New Relic monitoring in Production correctly reflects application activity. | PQVP Sprint 3 | 2017-02-20 15:52 | TechArch
PQVP-146 | Bug | User Profile - page does not re-focus to reported errors | Done | When attempting to create a user profile, I entered all the required fields and left the first name and last name blank. When I scrolled to the bottom of the form and clicked Save, the page appeared to stay put. I had to scroll up to the top of the page to see that I had received an error. Page should take me to the reported error. Now, if we had inline editing and were not requiring non-required fields, this may have been a non-issue. | PQVP Sprint 3 | 2017-02-20 17:29 | Developers
PQVP-147 | Bug | Login - Manage Profile and Logout links display in header of Login page | Done | As a Android Mobile user using the Chrome browser, I went to the Login page. The page loads with the Manage Profile Link and Logout Link in the upper left hand corner of the blue header. Per the wireflows, I would not expect to see either of those links on the Login page. Related to this, if I am using a PC I see the following behavior. If I login and get to the Landing Page and then hit 'Back' , the Manage Profile and Logout links pop up on the Login page in the header and they should not be there. | PQVP Sprint 4 | 2017-02-20 18:19 | Developers, Sprint4Planning
PQVP-148 | Bug | User Profile- Successful save of new profile should show Profile Confirmation page | Ready | After I successfully saved a new profile on the User Profile page, I expected to see a Profile Confirmation page, per wireframes. Instead, selecting Save took me to the landing page. The Profile Confirmation should have an Ok button preceded by the message: Thank you for registering. Your profile has been saved. Clicking Ok should then take me to the user landing page |  | 2017-02-21 12:35
PQVP-149 | Story | Integrate User Profile features | Done | *Acceptance Criteria* Integrate User Profile features (76/77/79/80) into application Coordinate FE/BE - resolve integration differences | PQVP Sprint 3 | 2017-02-21 12:46 | Developers
PQVP-150 | Story | Integrate Publish ad hoc notifications to subscribers | Done | *Acceptance Criteria * Integrate Publish ad hoc notifications to subscribers (96) Coordinate FE/BE - resolve integration differences | PQVP Sprint 3 | 2017-02-21 12:52 | Developers
PQVP-151 | Story | Integrate Admin track, analyze, and visualize notification data (admin landing page) | Done | *Acceptance Criteria * Integrate Admin track, analyze, and visualize notification data (97) Coordinate FE/BE - resolve integration differences | PQVP Sprint 3 | 2017-02-21 13:01 | Developers
PQVP-152 | Story | Integrate User Landing Page | Done | *Acceptance Criteria * Integrate User Landing Page (102) Coordinate FE/BE - resolve integration | PQVP Sprint 3 | 2017-02-21 13:06 | Developers
PQVP-153 | Story | Integrate Receive notifications via my chosen notification | Done | *Acceptance Criteria * Integrate Receive notifications via my chosen notification methods (98) Coordinate FE/BE - resolve integration | PQVP Sprint 3 | 2017-02-21 13:10 | Developers
PQVP-154 | Story | Integrate geo-location capture/last known location | Ready | *Acceptance Criteria * Integrate geo-location capture/last known location (104) Coordinate FE/BE - resolve integration |  | 2017-02-21 13:16 | Developers, Mobile
PQVP-155 | Story | As a product owner, I want the application to reflect the agreed logo and branding. | Done | *Acceptance Criteria* * Header should be larger, with an icon in the upper right and a larger title * Remove footer * Increase font size and thickness for header links |  | 2017-02-21 14:56 | Developers, UI/UX
PQVP-156 | Bug | User Profile- Additional text (this will be your...) should be displayed after text input not before | Done | On User Profile, this text is displayed before or next to text input. It should be under, per wireframes: - (this will be your login Username) - (this number will be used for text alerts) - This will be used to send you notifications based on your residential location. |  | 2017-02-21 16:01
PQVP-157 | Improvement | User Profile - Hitting esc should act like cancel | Done | When in Create User Profile and Manage Profile, hitting the esc key should function like hitting the Cancel button. Currently, hitting esc causes no action |  | 2017-02-21 16:32
PQVP-158 | Bug | Clicking the logo in the header should take user to the landing page | Done | When a user clicks the logo in a page header, it should take them to the Landing Page. Currently, clicking the logo has no function. | PQVP Sprint 4 | 2017-02-21 16:34 | Developers
PQVP-159 | Bug | Landing Page - Non-Emergency Typo in Event Type drop down values | Done | Non-Emergency is spelled wrong in the Event Type drop down list of values. It is spelled Non-Emervecy instead of Non-Emergency | PQVP Sprint 3 | 2017-02-21 16:37 | Developers
PQVP-160 | Bug | Landing Page - Missing 'No Events Found' message | Done | On the Landing Page, if there are no events/notifications to display based on the filters, the page should display a message to the user that there are 'No Events Found' per the wireflow. | PQVP Sprint 3 | 2017-02-21 16:39 | Developers
PQVP-161 | Story | As a Product Owner, I want a sample user available in the database so that evaluators can log in to an existing account to see a populated landing page. | Done | *Acceptance Criteria* * A sample user exists in the production database. * Notification information exists in the production database with historical information about notifications sent to the sample user. | PQVP Sprint 4 | 2017-02-21 17:03 | Developers
PQVP-162 | Story | As a DevOps engineer, I want to automate production deployments. | Done | *Acceptance Criteria* * Jenkins deployment scripts have been created for the Production environment. * Production deployments using the scripts have been tested. | PQVP Sprint 3 | 2017-02-21 17:05 | DevOps
PQVP-163 | Story | As a user, I want geo-location to be an opt-in feature, so I won't be prompted for my location unless I have consented to that. | Ready | *Acceptance Criteria* * User profile page allows user to indicate whether they want the system to capture their location. Initially this is unselected, to provide an opt-in model. * When user logs in to application from a device that supports geo-location, the application captures their current location if they have opted in to location capture. * If the user has not opted in to location capture, the application does not attempt to capture their location. *Notes* If we implement this after we are in production, there are data conversion issues to be considered -- do we set the flag to "opted in" for existing users? |  | 2017-02-21 17:50 | Developers, Mobile
PQVP-164 | Story | As a user, I want to receive event notifications when any part of the event is within 50 miles of me, so notifications are more accurate for events with a large footprint. | Ready | *Acceptance Criteria* * Automated and ad hoc events that occur within 50 miles of my location result in my being notified by my selected notification methods. * Automated and ad hoc events that occur more than 50 miles from my location do not result in my being notified. *Notes* * Acceptance criteria for this story are the same as for PQVP-98, but the definition of "event location" in the notes is different. * Be aware that the distance requirement may change to something other than 50 miles, or to a value the user can set. * For purposes of this story, the +*user's*+ location is a single point. If all we know is a ZIP code, that point would be the centroid of the ZIP code. If we have a more precise location (via more comprehensive data collection or geo-location), that location would be used instead. Future stories may refine this to treat a ZIP code as a region. * For purposes of this story, the +*event*+ location is a region, if the data source provides one. Otherwise, the event location is a single point, which may be the centroid of a ZIP code for ad hoc notifications. * The content of the notification should be as indicated in https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/PQVP%20Notification%20Text.docx. |  | 2017-02-21 17:56 | Developers, NotificationCriteria
PQVP-165 | Story | As a user, I want the application to inform me of any ongoing events I should know at the time I create or update my profile, so I can be aware of immediate dangers. | Ready | *Acceptance Criteria* * When a user saves a profile, whether a new one or an previously existing one, the application checks for events currently in progress near that user's profile location. * If any such events exist, the application notifies the user of the events via the user's chosen notification methods. The application also displays information about the event in the web app. *Notes* We could decide to be selective about what profile changes trigger immediate notifications -- e.g., only a location change. However, we should err on the safe side and check immediately for any profile change. |  | 2017-02-21 18:05 | Developers, UI/UX
PQVP-166 | Sub-task | Front End Tasks | Done |  | PQVP Sprint 3 | 2017-02-21 19:21
PQVP-167 | Sub-task | Back End Changes | Done |  | PQVP Sprint 3 | 2017-02-21 19:22
PQVP-168 | Sub-task | Front End Changes | Done |  | PQVP Sprint 3 | 2017-02-21 19:22
PQVP-169 | Sub-task | Back End Changes | Done |  | PQVP Sprint 3 | 2017-02-21 19:23
PQVP-170 | Sub-task | UI Page Styling | Done | Ensure page look/feel matches wireframes and displays as expected on phones | PQVP Sprint 3 | 2017-02-22 08:21
PQVP-171 | Sub-task | back end changes to persist generated event | Done | back end changes to persist generated event | PQVP Sprint 3 | 2017-02-22 08:22
PQVP-172 | Bug | Publish Notification- I am able to type more than the allowed 135 characters | Done | In Notification Text on Publish New Notification page, I was able to type more than the allowed 135 characters, causing the counter to go negative. Per agreement with PO and UX/UI designer, typing should stop at 135 characters (0 characters remaining). | PQVP Sprint 3 | 2017-02-22 11:10 | Developers
PQVP-173 | Bug | Create User Profile - form reset is inconsistent in regards to Your Information title | Ready | Start at the Login Page. Click Create User Profile. Form loads displaying the Your Information title as expected. Cancel out of form. Click Create User Profile again and form resets such that it does not show the Your Information title anymore. You have to refresh at the Login page to have the form reset to show Your Information again. |  | 2017-02-22 13:59
PQVP-174 | Story | As a user, I want the application to store my most recent geo-location frequently, so it will have all the information necessary to send me relevant event information. | Ready | *Acceptance Criteria* * If the user is using the native mobile app, has the app open in the foreground or background, and is logged in from the mobile app, the application updates the user's geo-location at least every 10 minutes, if available. * Application stores the user's most recent geo-location and the date/time at which it was stored. *Notes* * The application only stores the most recent location, not a history of locations. * This * This is one of the starter stories for our mobile app test. |  | 2017-02-22 15:50 | Developers, Mobile
PQVP-175 | Sub-task | Event Notifications Persistence for Automated Alerts | Done | Currently we have identified the following changes for event notifications * removing not null requirements for zip code * creation of system admin user | PQVP Sprint 3 | 2017-02-22 18:24
PQVP-176 | Sub-task | Add automated notification alert and persistence to flood and weather type | Done | Currently we have automated alerts sending for SMS and Email for fire events need to model for flood and weather type events | PQVP Sprint 3 | 2017-02-22 18:26
PQVP-177 | Bug | Login and User Profile Page (iphone 5)- Header display | Done | The links in the header of the app (Manage Profile and Logout) wrap to the next line when app is viewed on an iphone 5, making header pretty wide and covering the top of the Login and User Profile pages- see attachments for a visual. They shouldn't wrap. A couple of notes: - This is also an issue for other pages available in current build. - When I view the app on my laptop, I no longer see Manage Profile and Logout links on the Login page. On my iphone 5, I do. | PQVP Sprint 4 | 2017-02-23 08:59 | Developers, Sprint4Planning
PQVP-178 | Bug | Login - duplicative error messaging | Ready | Users receive 2 differently formatted error messages for the same error. To reproduce, take the following steps from the Login Page: -Click into Password field without clicking into or typing anything in the username field. -Enter Password -Hit Enter or click Login -User sees a pop up error message that says "Please fill out this field" or -Enter username -do NOT tab to or enter anything in the Password field. -Click enter or Login -User sees a pop up error message that says "Please fill out this field" Only messages I expect to see per the wireflows are the red message telling me that "You must enter a valid password" or "You must enter a valid username" Possible connection with defect #121 |  | 2017-02-23 12:05
PQVP-179 | Bug | User Profile - copying Password to Confirm Password fails | Done | Copying a password from the Password field to the Confirm Password field does not work. When I paste my password into the Confirm Password field it seems to append several masked characters and then reports that my passwords must match | PQVP Sprint 3 | 2017-02-23 12:21
PQVP-180 | Story | As a user, I want the application to alert me of events near my current location even if I am not in the application, so event information will be more relevant to me. | Ready | *Acceptance Criteria* * If user has installed the mobile app and has ever logged in from it, push notifications are sent to that user based on their most recently known location. * Notifications appear as push notifications native to the client platform. * Notifications appear whether the app is not running, running in the background, or running in the foreground. *Notes* * This is one of the starter stories for our mobile app test. * Not sure if there's a technical limitation that we can only collect location when the app is open in the background or foreground. For purposes of this story, it shouldn't matter -- this is about using that location for alerts. |  | 2017-02-23 13:11 | Developers, Mobile
PQVP-181 | Story | As a user, I want to be able to log in to the mobile application to enable functionality specific to me. | Ready | *Acceptance Criteria* * Mobile application allows user to login. * Mobile application requires entry of a username (email address) and password to log in. * If user cannot be authenticated, no further functionality is available. * Upon successful authentication, application persists device identifying information for use in push notifications. *Notes* * This is one of the starter stories for our mobile app test. |  | 2017-02-23 13:33 | Developers, Mobile, UI/UX
PQVP-182 | Bug | Data sources - polling should be every 6 hours | Done | Right now, we poll our weather/fire/flood sources every 1 minute. The user stories indicate they should poll every 6 hours. | PQVP Sprint 4 | 2017-02-24 10:50 | Developers, Sprint4Planning
PQVP-183 | Story | Landing page tweaks | Done | *Acceptance Criteria* * Change title to National Event Notifications * Rename "Admin_E" to "Emergency Alert", "Admin_I" to "Non-Emergency Alert" * Change icons to be specific to event type * Remove ZIP codes section in info pane for automated events * Move filters to be side by side, not above one another | PQVP Sprint 3 | 2017-02-24 11:04 | Developers, UI/UX
PQVP-184 | Bug | Admin Landing - inconsistent results based on device/browser | Done | Below is a list of what shows/does not show on the Admin Landing page from various devices/browsers: -Mac Safari: no events, no map -PC IE11: no events, no map -PC Firefox: events and map display -PC Chrome: events and map display -iPad Chrome: no events, no map -iPhone Safari: no events, no map -Android Chrome - events display but unable to get to the notification details or map | PQVP Sprint 4 | 2017-02-24 14:18 | Sprint4Planning
PQVP-185 | Bug | User Profile page (IE)- Can't differentiate placeholder text from that entered by user | Ready | On the User Profile page in IE, I expected the placeholder text in the Text Input fields to be smaller font and gray. Currently, it has the same font, font size, and color as the labels and as the text entered by the user, so it's hard to differentiate. Note that the wireframes do not show the placeholder text, so please check with Gabe on what to update to. |  | 2017-02-24 16:52
PQVP-186 | Bug | Admin Landing Page - Map is showing incorrect location | Done | I published an Ad Hoc notification for the 95677 zip code which is in Rocklin CA. However, when the event displays on the Admin Landing Page, the map shows Sydney Australia. There is no pin on the map either. | PQVP Sprint 3 | 2017-02-24 17:12 | development
PQVP-187 | Bug | Admin Landing Page - title is incorrect | Done | Before 2/24 deploy, the title on the Admin User Landing Page was Event Notifications. It now shows as Landing.Admin.Title instead of Event Notifications. | PQVP Sprint 3 | 2017-02-24 17:28 | development
PQVP-188 | Bug | Create User Profile - left side of form being truncated | Done | The left side of the form seems to truncate slightly. The best way to see this is to look at the notification type check boxes as the left side of the box is not visible. |  | 2017-02-24 17:32 | development
PQVP-189 | Bug | Manage Profile- Password and Confirm Password fields are blank. | Ready | On the User Profile page when accessed from Manage Profile, all previously saved info is carried over except for the password and confirm password fields. I expected these two text input fields to show the password as hidden (......) so the user is not led to believe they need to re-enter, or forced to re-enter if they accidentally clicked in one of these two fields. |  | 2017-02-24 17:34
PQVP-190 | Bug | Create User Profile - Inconsistent Registration Notifications | Done | Per the wireflows, when a user successfully registers, they should be taken to the Registration Confirmation page. Currently, if a user selects to receive notifications via email, they do not receive an email confirmation. They receive no confirmation. However, if they select to receive notifications via text, they do receive a text confirmation. Users should be taken to the Registration Confirmation page, they should not receive a text or email confirmation. | PQVP Sprint 4 | 2017-02-24 17:40 | development
PQVP-191 | Bug | Create New User - No Scroll Bars and Tabbing does not work in Mac Safari | Done | When navigating the Create New User page on Mac Safari, I am not able to tab from field to field or see the Cancel / Save buttons. The form allows me to tab through all the field up until the notification types. Once you hit notification types, you can no longer tab to the next field and the there is no scroll bar to actually get to the Cancel / Save buttons. | PQVP Sprint 4 | 2017-02-24 17:51 | development, Sprint4Planning
PQVP-192 | Bug | Notification Details - Not displaying the number of users notified | Done | Log in as Admin user and default to Admin Landing Page. Click on an info icon on an Event from the Event List. Notification Details page comes up but the # of users notified is not populated. | PQVP Sprint 3 | 2017-02-24 18:16 | development
PQVP-193 | Improvement | Publish New Notification - description for 15 mile radius of zip code for notifications | Done | Include words on the Publish New Notification page that notifications will go out to users within a 15 mile radius of the designated zip codes. If you don't know this is our business rule then it seems odd to send a notification to a specific zip code and have people outside of that zip code receive it. *Note* Change the text that currently reads: {quote}Enter one or more zip codes to issue this notification to. Multiple zip codes should be separted by commas.{quote} to: {quote}Enter one or more zip codes affected by this event. Multiple zip codes should be separated by commas. Note that users within 15 miles of these ZIP codes will receive notifications about this event.{quote} | PQVP Sprint 4 | 2017-02-24 18:55 | Sprint4Planning
PQVP-194 | Bug | Admin Landing Page- Notification details do not refresh when a new event is selected | Done | On the Admin Landing page, if I select the icon to display the Notification Details for one event and then select another event, the Notification Details area does not update to reflect the event selected. It should. | PQVP Sprint 3 | 2017-02-24 19:28 | development
PQVP-195 | Bug | Publish New Notification- Typo ('separated'). Capitalize c in 'codes' | Done | On the Publish New Notification page, 'separated' is misspelled. c in codes in label should be capitalized. | PQVP Sprint 3 | 2017-02-25 09:49 | development
PQVP-196 | Story | As an admin user I would like to see more information about my list events | Done | *Acceptance Criteria* * Change the text on the event list to better reflect what's going on with the event. Use the Event Title from the [PQVP Notification Text¦https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/PQVP%20Notification%20Text.docx] document to determine what the new text should say instead of Flood/Fire/Weather/Emergency/Non-Emergency. * Update the Notification Details to display the Notification text indicated in the document instead of Flood/Fire/Weather/Emergency/Non-Emergency. * Change the notification messages to reflect the changes as well, per the [PQVP Notification Text¦https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/PQVP%20Notification%20Text.docx] document. *Note* Be aware of word wrap concerns. It would be better to let the text be truncated than to throw off the format of the list. | PQVP Sprint 4 | 2017-02-25 14:18 | Developers, UI/UX
PQVP-197 | Bug | Site icon in address bar should be app logo | Done | When I look at the MyCAlerts.com site, it shows a US flag in the browser address bar. It should show the app logo instead. | PQVP Sprint 3 | 2017-02-25 14:27 | Developers, UI/UX
PQVP-198 | Improvement | As a developer, refactoring event notifications for automated notifications to remove duplicate function | Ready | The construction of event notification for persistence in the database shares function for flood, fire and weather events. The event notification construction can be refactored to remove duplicate function during construction. |  | 2017-02-25 14:27
PQVP-199 | Improvement | As a developer, refactoring automated email notifications to utilize BCC for performance and efficiency | Done | During processing of events for notifications (fire, flood and weather) the email service is sent for each individual address. Currently we have the ability to send to multiple emails utilizing the TO: address, we need to verify if sending batches of emails will show other users addresses within same area. If other users email addresses are displayed as additional TO: addresses we need to implement the function of utilizing the BCC address for sending batch alerts | PQVP Sprint 4 | 2017-02-25 15:36 | Sprint4Planning
PQVP-200 | Bug | Publish New Notification - Link takes me to new page instead of replacing map | Ready | Per the v3 wireflows, when a user clicks the Publish New Notification link, that page should replace the map on the Admin Landing Page. Instead, the user is taken to a new page. |  | 2017-02-25 20:41
PQVP-201 | Bug | Publish New Notification - No confirmation screen on Send or Cancel | Ready | If the admin clicks SEND on Publish New Notification, they should be taken to a Publish Confirmation page. To return to the Admin Landing Page, they click OK. If the admin clicks CANCEL on Publish New Notification, they should be taken to a similar confirmation screen to confirm the cancel. This screen should say â€œAre you sure you want to cancel this notificationâ€ YES/NO -No returns Admin back to previous screen to finish composing the Ad Hoc message. -Yes returns Admin to list/map view. |  | 2017-02-25 20:47
PQVP-202 | Bug | Publish Notification- Sent text is missing "Emergency alert: " or "Non-emergency alert: " | Done | When an adhoc notification is sent, the text of the notification sent should be "Emergency alert: " or "Non-emergency alert: " (depending on the event type chosen) followed by the message entered by Admin on the Publish Notification page. "Emergency alert: " or "Non-emergency alert: " is not getting appended. *Note* Please align all notification text, including email subject line, to the rules defined in https://cgisacramento.atlassian.net/wiki/download/attachments/1907298/PQVP%20Notification%20Text.docx. |  | 2017-02-25 21:17 | development, sprint, sprint4planning
PQVP-203 | Bug | Notification Details- Use external source name for Sent By | Done | In the Notification Details: For fire, use 'Active Fire Boundaries (USGS GeoMAC)' For flood, use 'River Gauge - Current and Forecast (NOAA)' For weather, use 'Weather Hazards (NOAA)' | PQVP Sprint 4 | 2017-02-26 09:04
PQVP-204 | Bug | As a developer, refactoring APICallerServiceTest removing unexpected failed tests caused by networking | Done | Refactoring to correct observed failing tests utilizing connection to google and emergency data end points. Additionally, refactoring test cases for fire, flood and weather events checking for Level.INFO containing "Event" string this is caused by variation in data returned from polling the emergency event data end points during tests. | PQVP Sprint 3 | 2017-02-26 14:53
PQVP-205 | Bug | User Landing Page - events show oldest to newest | Done | Notifications are being displayed oldest to newest instead of newest to oldest like on the Admin User Landing page. | PQVP Sprint 3 | 2017-02-26 16:31 | development
PQVP-206 | Bug | Admin Landing Page - loading event and filtering very slow | Done | The response time to initially load and then filter events - particularly Emergency and Flood is very slow. Believe this defect to be related to the large number of Flood alert SMS messages that were being sent out. | PQVP Sprint 3 | 2017-02-26 17:22 | development
PQVP-207 | Bug | Flood Notifications - Messages being sent every time we poll even through already noticed | Done | Flood notifications were turned on and a stream of notifications were sent. Seems notifications were being sent for each event upon each polling even though some of those notifications had already been sent out. Per discussion with PO, a new notification should only be sent for new events. Existing events with updates to the details will not trigger someone who has already been notified to be notified again. Someone who signed up since the original notification and who has not been previously notified, will receive the updated notification. | PQVP Sprint 3 | 2017-02-26 19:37 | development
PQVP-208 | Bug | Flood Alerts - Messages reference "our site" instead of actual site link | Done | When clicking into the Notification Details, flood alerts include the text: "Emergency alert: Flood near Mokelumne River in your area. Please log in at <our site> for more information" The reference to <our site> needs to be updated to the actual link. | PQVP Sprint 3 | 2017-02-26 22:18
PQVP-209 | Sub-task | As a registered user , prompt for push notifications | In Progress | * FCM library integrated * request and save token * this has to work within angular environment (might be tricky) | PQVP Sprint 3 | 2017-02-27 10:09
PQVP-210 | Sub-task | Unsubscribe from push upon change of preference | Done | * Nothing is required on front end * Backend will not send a push due to Profile's Unchecked value for Push Notifications | PQVP Sprint 3 | 2017-02-27 10:23
PQVP-211 | Sub-task | Browser to allow and capture approximate position | Ready | * Users must allow their position to be taken - position will always be approximate , not reliable * Send data to an API |  | 2017-02-27 10:25
PQVP-212 | Bug | Notifications - email alerts not being received. | Done | Users signed up to receive email notifications are not receiving emails. | PQVP Sprint 3 | 2017-02-27 11:46
PQVP-213 | Bug | 508 Compliance: Missing language tag in HTML | Done | This is the only 508 compliance error we are getting using our compliance tool ACTF aDesigner. See screenshot for details. | PQVP Sprint 4 | 2017-02-27 12:08 | 508_Compliance, Sprint4Planning
PQVP-215 | Story | As a user, I want to only receive notifications of events that are within 15 miles of me. | Done | *Acceptance Criteria* * Users are notified via preferred notification methods of events within 15 miles of them. * Users are not notified of events greater than 15 miles from them. | PQVP Sprint 4 | 2017-02-27 16:21 | Developers, Sprint4Planning
PQVP-216 | Bug | When address is invalid, adhoc Notification (email and text) are not sent to user with same zip code from notification | Ready | Logged in as admin, I sent an adhoc emergency notification to zip code 53719. I had a user set up with email address zip code 53719 and a phone number- all notification methods selected. User did NOT receive a text or an email. I also tried an adhoc non-emergency notification and it was also not received by user. Note: phone number and email address are both valid. After further testing, the email and text do get sent if I update the rest of the address information to a valid address within zip code (it was not a valid address before). |  | 2017-02-27 17:36
PQVP-217 | Bug | Ad Hoc Notification - Email recipients displayed in To line of email | Done | Users receiving an emailed Ad Hoc notification are able to see the list of recipients in the To line of the email. This should be not be the case. | PQVP Sprint 4 | 2017-02-27 17:59 | Sprint4Planning
PQVP-218 | Improvement | Add renotifications if significant event information changes | Ready | Right now, our design is such that, if an automated source tells us about the same event twice, we won't send a new notification to someone we've already notified of that event. However, we may want to send another notification if key information about the event has changed (e.g., the region affected by a wildfire has increased). This would involve us determining, for each automated source, which columns should trigger a renotification and which ones shouldn't. |  | 2017-02-27 19:55 | Developers, NotificationCriteria
PQVP-219 | Improvement | Notify people who have registered since the event was first received, if it is received again. | Ready | Current design is that we'll only send one "wave" of notifications related to a given event (unless the event information changes). That means that if we receive the same event twice, unchanged, and a new user registers between the first and second time we receive it, they won't be notified of the event. Recommend changing our approach so that every time we receive an event, we identify everyone affected by that event, minus everyone we've already notified about the event. What remains is the list of people to notify. Note that there's a separate improvement logged about renotifying people if the event has changed. If we implement that, we would notify everyone affected once the event has changed, not just the newer registrants. |  | 2017-02-27 22:00 | Developers, NotificationCriteria
PQVP-220 | Sub-task | Store and update firebase token via api | In Progress | User table needs to have a column that will support a string that can be as long as 500 characters. API authenticated user PUT : /user/fcmtoken Body: {fcmtoken: "KFJDKJFKSDLJFSDKLFJLSDKJ"} | PQVP Sprint 3 | 2017-02-28 11:35
PQVP-221 | Improvement | As an admin user, I would like to to have a faster and more responsive landing page | Done | One of the key pieces of feedback we have received from each user we've put the app in front of was that the landing page (the list and map construct) was painfully slow to load. In some cases it took as long as 20-24 seconds to load, which can give the appearance of the app actually being broken. One way we could significantly improve usability for the app would be to improve the performance of this page by reducing the amount of time it takes for the list elements to load and for the map to render the first event in the list. | PQVP Sprint 4 | 2017-02-28 12:17 | Sprint4Planning
PQVP-222 | Bug | Manage User Profile - Unfriendly error message when change email address to a duplicate email address. | Ready | Steps to reproduce: 1. create a user with email blah@blah.com 2. create another user with email blah2@blah.com 3. login as blah2@blah.com 4. click manage profile 5. edit email to be blah@blah.com 6. notice that the error message is not user friendly. instead it says "Constraint violation <email>. Unable to Save: Duplicate entry 'blah@blah.com' for key 'email'" |  | 2017-02-28 12:33
PQVP-223 | Improvement | Reduce number of flood notifications | Done | Reduce number of flood alerts -- recommend not sending alerts for flood watches, just flood warnings. | PQVP Sprint 4 | 2017-02-28 13:09 | Developers, Sprint4Planning
PQVP-224 | Improvement | Change language of "password is required" message on login page. | Done | Message should not allude to the password requirements (length, etc). Should just say "You must enter a valid password." | PQVP Sprint 4 | 2017-02-28 13:21
PQVP-225 | Sub-task | Send a notification to user's device - web push | Ready | Backend to send using standard HTTP POST Firebase server KEY: Add header Authorization value: key=AAAA8XU5NgQ:APA91bEfETw0rTo7J1exWlzARff99f_SlyI1SVZywP_LGsLBOMAuVGbclayJGIfVRRb624N87-CP0MY6TmHR2jgBLU5irF7T4N40cFanF6or6pxLEGYMEisWilC6GjOL2Wx-0BXt8LRv Body: { "notification": { "title": "Alert", "body": "There is a flood warning" }, "to" : "f_g7MGEGby8:APA91bFU5iK4hdDjJ1qV4gHYcSJ-xU-4GLSiXT3zJxWthYQ25V3Tx_nj23Hl_SAmjLo4EBn_TZoA1mnCFIXcI2Y6Q4DabDT6RcTljqjcb-oAEMyI9mzzYk_CQTIje6-2Hw7JOJ96yfh1" } Successful RESPONSE {"multicast_id":7733210718836532357,"success":1,"failure":0,"canonical_ids":0,"results":[{"message_id":"0:1488314451590142%cc9b4facf9fd7ecd"}]} The To field is the FCM token we store. Title is optional | PQVP Sprint 3 | 2017-02-28 14:30
PQVP-226 | Improvement | As a user, I want to be able to set a threshold distance, so I can dictate how close an event has to be in order for the application to notify me. | Ready | *Acceptance Criteria* * User can set a threshold distance in their user profile. * The distance defaults to whatever the application default distance is (currently 15 miles). * The distance is a required field. * When the application checks to see whether the user should be notified of an event, it uses the user-specified distance to determine proximity. |  | 2017-02-28 20:28 | Developers, UI/UX
PQVP-227 | Improvement | As an Administrative user, I want to be able to add other Administrative users as well as to update my own profile, so we can track which user generated each notification. | Ready | *Acceptance Criteria* * Administrative users have access to modify name, username, and password information. * Name, username, and passwords are required. * Password validations are the same as for end user. * Administrative users can create user profiles for new Administrative users. |  | 2017-02-28 20:32 | Developers, UI/UX
PQVP-228 | Improvement | As an Administrative user, I want to see more visualizations of event and notification data, so that I can better understand my users' locations and needs. | Ready | *Acceptance Criteria* * Administrative Users have access to visualize aggregate data (for instance, overlap between selected events, location of users notified about an event, etc). * Administrator Landing page includes additional filtering options, such as date or location. * Administrator Landing page provides more information about what types of notifications were sent for each event. |  | 2017-02-28 20:35 | Developers, UI/UX
PQVP-229 | Improvement | As a user, I want to follow MyCAlerts on Twitter, so I can follow events without registering or making my location known. | Ready | *Acceptance Criteria* * Each event received is issued as a Tweet. *Notes* Need to determine whether this has value given that it wouldn't be location-specific. |  | 2017-02-28 21:03 | Developers
PQVP-230 | Improvement | As a user receiving a notification, I want a quick way to unsubscribe from notifications so I can easily opt out of the service. | Ready | *Acceptance Criteria* * Email notifications include an embedded "unsubscribe" link in email body. * Clicking the "unsubscribe" link takes user to a web page that gives them the ability to turn off all notifications. * SMS notifications include text reading, "Reply STOP to unsubscribe." * If user responds to SMS with STOP message, that user is unsubscribed from all notifications. *Notes* * It's not clear whether there's a reliable way to offer an unsubscribe option in the context of push notifications. * Can consider whether an SMS STOP message should only turn off SMS alerts as opposed to all alerts. |  | 2017-02-28 21:09 | Developers
PQVP-231 | Improvement | As a user, I want the application to display my location on a map so I can confirm that it located me correctly. | Ready | *Acceptance Criteria* * When the user enters or updates their address information on the User Profile page, the application displays the entered location on a map. * If user determines the displayed location is not correct, they can modify their address information to fix the issue. * On a device that supports location services, the application uses a "follow" model to show where it believes the user to be. This will inform the user of whether their location will be accurately used by our service. |  | 2017-02-28 21:12 | Developers, UI/UX
PQVP-232 | Improvement | As a user, I want the application to alert me if I have entered an invalid ZIP code. | Ready | *Acceptance Criteria* * After user enters a ZIP codes, validate that ZIP code against a known list of good (meaning acceptable to the post office) ZIP codes. * If the ZIP code is not on the list, the application disallows the user from saving. *Notes* Need to determine if this should really be a hard edit -- user may only want services based on geolocation, not on profile. |  | 2017-02-28 21:14 | Developers, UI/UX
PQVP-233 | Improvement | As a team member, I want to cross-platform testing using Selenium Grid | Ready |  |  | 2017-02-28 21:15 | Developers
PQVP-234 | Improvement | Provide testers / state evaluators with a mock event service | Ready | People testing or evaluating our system are somewhat limited in their ability to test -- ad hoc events can always be generated but they won't be able to test automated emergency events. This improvement contemplates a mock service, which evaluators could toggle to from a settings or labs option, that would create "fake" events for testing purposes. |  | 2017-02-28 21:16 | Developers, UI/UX
PQVP-235 | Bug | User Profile - Remove push notification checkbox | Done | *Acceptance Criteria* * Push notification option is not available on user interface. * No push notifications are sent. * Remove reference to push notifications on login page. Where the text currently says "email, text message, or push notification", change to "email or text message". | PQVP Sprint 4 | 2017-03-01 11:21 | Developers
PQVP-236 | Bug | SSL handshake fixes | Done | Intermittent SSL handshake issues keep users from attaching -- problems seen on Safari on Mac, and Firefox on Windows. | PQVP Sprint 4 | 2017-03-01 11:30 | Developers
PQVP-237 | Bug | Login - IE11 no longer shows invalid username/password error | Done | Attempt to log in with an invalid username/password then click log in. User no longer receives "Incorrect username/password combination" error box. | PQVP Sprint 4 | 2017-03-01 11:32
PQVP-238 | Bug | Increase token timeout to 24 hours | Done | Current timeout is 1 hour. Increase to 24. | PQVP Sprint 4 | 2017-03-01 12:03 | Developers
PQVP-239 | Bug | User Profile - Disable email address update | Done | Users should not be able to update their email address on the User Profile page, except during initial registration. | PQVP Sprint 4 | 2017-03-01 12:05 | Developers, UI/UX
PQVP-240 | Bug | Admin Landing Page - Styling issues | Done | - PC/Chrome, PC/Firefox, PC/IE11: Need to scroll to see bottom of notification details page - PC/Chrome, PC/Firefox, iPhone 5, iPad: where more than 4ish zip codes are entered (the example in screen print has 20), the box does some funky things to acco | PQVP Sprint 4 | 2017-03-01 13:12
PQVP-241 | Bug | Login Page - Styling Issues | Done | #NAME? | PQVP Sprint 4 | 2017-03-01 13:14
PQVP-242 | Bug | User Profile Page - Styling Issues | Done | - PC/IE11: the Dropdown button covers the longer state names - not wide enough for "California" | PQVP Sprint 4 | 2017-03-01 13:15
PQVP-243 | Bug | Error Handling - forms do not reset to section of form where error occurs | Ready | If you fill out the user profile form and skip over a required field and click Save, an error message pops up but the user is forced to scroll up to find the message as opposed to having the form scroll back up to where the error exists. |  | 2017-03-01 14:41
PQVP-244 | Improvement | Password management improvements | Ready | Improve our password standards and approach: * Require passwords to be at least 14 characters, and accommodate at least 50 characters. * Track the last successful and last unsuccessful login attempt. * Retain the last 24 passwords and prohibit users from using one of their last 24 passwords. * Store the date the password was last changed and enforce password aging requirements. |  | 2017-03-01 14:42 | Developers, Security
PQVP-245 | Bug | Event List - Remove Zip Code label from Automated messages | Done | Zip code label on the event list should be there for ad hoc events but not automated messages as the automated messages do not include zip code information. | PQVP Sprint 4 | 2017-03-01 14:57
PQVP-246 | Bug | Update User Profile - Don't force notification type | Ready | When you go to update a user's profile, do not force them to check a notification type. This will provide users with a way to stop their notifications. Create User Profile should force you to enter a notification type. |  | 2017-03-01 16:03
PQVP-247 | Improvement | User Profile - improve handling of notification method checkboxes | Done | * In create mode (i.e., when the user is registering), default the Email checkbox to checked. Leave the SMS checkbox unchecked by default. Users can change either of these values. * Both in create and update mode, turn off the "requiredness" of the notification method checkboxes. Users are able to save without checking either box. | PQVP Sprint 4 | 2017-03-01 17:23 | Developers
PQVP-248 | Improvement | Publish Notification - default notification type to Emergency | Done | When the user first accesses the Publish Notification page, the Emergency radio button should be pre-selected. That avoids the user attempting to save without selecting a notification type. | PQVP Sprint 4 | 2017-03-01 17:24 | Developers
PQVP-249 | Improvement | Add a "loading spinner" to the Admin Landing page, so it's clear the system is busy when loading alert events. | Done |  | PQVP Sprint 4 | 2017-03-01 19:17 | Developers
PQVP-250 | Bug | Create User Profile - Allowed to add user eve though passwords don't match | Done | When creating a user I entered a Password and then a different password in the Confirm Password field. I received an error reporting that the passwords do not match. However, when I clicked Save, the application still registered my user. | PQVP Sprint 4 | 2017-03-01 22:18
PQVP-251 | Bug | iPad Style Issues | Ready | Safari and Chrome on iPad always report back as mobile devices unless the user explicitly asks for the desktop site. -Horizontal ipad the event list looks fine but header stacks the menu links like Manage Profile, Publish New Notification, and Logout in upper right corner. -Vertical iPad the event list looks squished and the icon overlaps the messages. -iPad has the same 20 zip code squishing that Chrome showed â€“ vertical or horizontal |  | 2017-03-01 23:46
PQVP-252 | Bug | Publish New Notification - able to send duplicate messages due to slow send | Ready | After clicking send on the Publish New Notification page, there is a long enough delay in actually sending the notification that a user might hit Send again thinking they did not actually send it. A notification will be sent for each time the user clicks the send button. |  | 2017-03-02 11:42
PQVP-253 | Bug | Manage Profile link appears in the header of Manage Profile page. | Ready | Manage Profile link appears in the header of Manage Profile page. It shouldn't. |  | 2017-03-02 12:22
PQVP-254 | Bug | Publish New Notification - Carriage returns not counted in character counter | Ready | When typing a new message, the character counter does not count a carriage return as a character but the user is prevented from typing a full 135 characters because the carriage returns do seem to be counted at some level. |  | 2017-03-02 13:13
PQVP-255 | Bug | Publish New Notification - Can't send messages less than 5 characters | Ready | When attempting to send a notification with just "test" in the message, I am unable to get the message to send. |  | 2017-03-02 13:29
PQVP-256 | Bug | Publish Notification link appears in header of Publish Notification page | Ready | Publish Notification link appears in header of Publish Notification page. It shouldn't. |  | 2017-03-02 13:31
PQVP-257 | Bug | Publish New Notification - Android / Chrome allows me to type more than 135 chars | Ready | Using Chrome on Android, I am able to type more than 135 characters. The counter hits 0, resets to 135 and stops counting as I type. Upon send, the additional characters are truncated. |  | 2017-03-02 14:54
PQVP-258 | Story | As a user, I want a clearer picture of what the next steps are after I register. | Done | *Acceptance Criteria* * Instead of "No Events Found", the following text appears on the user landing page when no events exist there. Thanks for using MyCAlerts.com! As we identify events that impact you, we'll notify you based on your preferences, and also display the events here. | PQVP Sprint 4 | 2017-03-02 17:38 | Developers
PQVP-259 | Story | As a user or administrative user, I want the landing pages to clarify the distinction between "Emergency" alerts and other types which are emergencies (such as fires and floods). | Done | *Acceptance Criteria* * On the Publish page, the title reads "Publish New Ad Hoc Notification" * On the event list on the landing page, events say "Emergency alert (ad hoc)" and "Non-emergency alert (ad hoc)" rather than "Emergency alert" and "Non-emergency alert". * On the type filter on the landing page, options say "Emergency (ad hoc)" and "Non-emergency (ad hoc)" rather than "Emergency" and "Non-emergency ". | PQVP Sprint 4 | 2017-03-02 18:22 | Developers
PQVP-260 | Story | As a Product Owner, I want a way to automate multivariate testing to maximize key metrics. | Ready | *Acceptance Criteria* * Implement a tool that supports multivariate testing. *Notes* Some metrics we may want to direct this tool at: maximizing registrations, minimizing registration time. |  | 2017-03-02 22:31