## Digital Playbook Checklist
Notes
Play 1 - Understood What People Need |  | Artifact/Evidence | CGI Response
X | Early in the project, spend time with current and prospective users of the service | Interviews | We conducted persona interviews with various users in order to understand their needs and limitations.
X | Use a range of qualitative and quantitative research methods to determine people’s goals, needs, and behaviors; be thoughtful about the time spent | Personas | We conducted interviews and research to determine the needs of our users
X | Test prototypes of solutions with real people, in the field if possible | Usability testing | We conducted Usability testing with our users to gather their feedback
X | Document the findings about user goals, needs, behaviors, and preferences | Usability testing | Results of Usability testing were captured in user stories and prioritized
X | Share findings with the team and agency leadership | Usability testing | Usability test results were shared with the PM and other members of the team
X | Create a prioritized list of tasks the user is trying to accomplish, also known as “user stories” | Activity scenario planning | Users stories were used and prioritized
X | As the digital service is being built, regularly test it with potential users to ensure it meets people’s needs | Usability testing | We conducted Usability testing with our users to gather their feedback
Play 2 - Address the whole experience, from start to finish |  | Artifact/Evidence | CGI Response
X | Understand the different points at which people will interact with the service – both online and in person | Personas | Our persona interviews identified how our users would use the prototype based on their background, knowledge and preferences
X | Identify pain points in the current way users interact with the service, and prioritize these according to user needs | Usability testing | We accomplished this through user stories as well as results from usability testing
X | Design the digital parts of the service so that they are integrated with the offline touch points people use to interact with the service | Wireflows | Our wireframes provided a initial digital design and outlined how we expected users to interact with our prototype
X | Develop metrics that will measure how well the service is meeting user needs at each step of the service | Usability testing | Our user surveys provided feedback as to how well our prototype was meeting the needs of our users
Play 3 - Make it simple and intuitive
X | Use a simple and flexible design style guide for the service. Use the U.S. Web Design Standards as a default | US Web Design Standards | Our style guide was built using USWDS standards
X | Use the design style guide consistently for related digital services | US Web Design Standards | Our style guide was built using USWDS standards
N/A for POC | Give users clear information about where they are in each step of the process |  | Our prototype did not incorporate a process for which a user would need guidance as to where the users is.
X | Follow accessibility best practices to ensure all people can use the service | 508 Testing | We conducted testing for Section 508 of the Americans with Disabilities Act and WCAG 2.0 - We used the tool ACTF Designer for testing.
N/A for POC | Provide users with a way to exit and return later to complete the process |  | We do not collect enough data - users need to complete the minimum data in order to create a profile
X | Use language that is familiar to the user and easy to understand | Final prototype | Prototype pages are in English. We have a backlog story for future work to convert pages into Spanish given the percentage of the population of California which communicates in Spanish.
X | Use language and design consistently throughout the service, including online and offline touch points | US Web Design Standards | We used the US Web Design Standards. We tested to ensure that the application was at a 6th grade reading level of less using…..XXXX | Sixth grade reading level - app used by Gab
Play 4 - Build the service using agile and iterative practices
X | Ship a functioning “minimum viable product” (MVP) that solves a core user need as soon as possible, no longer than three months from the beginning of the project, using a “beta” or “test” period if needed | User stories, roadmap, JIRA | We had our MVP in 3 weeks time which met the core needs of our users. Backlog shows mature future roadmap for additional business value
X | Run Usability testing frequently to see how well the service works and identify improvements that should be made | Usability testing | We ran usability test throughout our process - incorporating feedback through users stories introduced in sprint.
X | Ensure the individuals building the service communicate closely using techniques such as launch meetings, war rooms, daily standups, and team chat tools | Communications | We used daily stand-ups and HipChat for regular team communications. In addition we had a war room with physical board. At the conclusion of each sprint the team performed a Retrospective to identify process/technical improvements
X | Keep delivery teams small and focused; limit organizational layers that separate these teams from the business owners | Team list | We worked with a small focus team. The team had direct access to the PM
X | Release features and improvements multiple times each month | roadmap to pipeline to builds, version control, deployment logs | Release features and improvements were reviewed as part of sprint planning each week. Test environment was available w/ early builds of the product.
X | Create a prioritized list of features and bugs, also known as the “feature backlog” and “bug backlog” | Jira backlog | We had an on going backlog in JIRA with a prioritized list of features. Backlog shows mature future roadmap for additional business value.
X | Use a source code version control system | GitHub | GitHub is the source of our code and versions. Main branch and integration branch management. GitHub tied into CD/CI process. Our Continuous Integration and Deployment section of the README provides further details.
X | Give the entire project team access to the issue tracker and version control system | GitHub and Jira | The entire team had access to GitHub and JIRA
X | Use code reviews to ensure quality | Describe the process - blurb. Peer review process? |  | Roberto has a paper. Photo album has examples.
Play 5 - Structure budgets and contracts to support delivery
X | Budget includes research, discovery, and prototyping activities | Spreadsheet blurb: created a "Login" application to validate design, code management, build, and deployment approaches | The team was given a budget which the PM tracked to
X | Contract is structured to request frequent deliverables, not multi-month milestones | Roadmap | Our roadmap provided a high-level structure for our major milestones
N/A for POC | Contract is structured to hold vendors accountable to deliverables |  | NOTE: CGI's contracts and partner agreements are typically deliverable-based or otherwise tied to performance
X | Contract gives the government delivery team enough flexibility to adjust feature prioritization and delivery schedule as the project evolves | Jira backlog (Work structured in sprints with check-ins, with backlog grooming and resequencing) | Based on our JIRA backlog we were able to adjust the work based on the responses of our PM as well as users | Cite examples where spike research development for a IOS app and push services was performed and then backlogged when it became clear they were not MVP viable.
X | Contract ensures open source solutions are evaluated when technology choices are made | Technology list | We used open source technology throughout.
N/A for POC | Contract specifies that software and data generated by third parties remains under our control, and can be reused and released to the public as appropriate and in accordance with the law |  | NOTE: CGI's partner agreements include similar language | Isn't this really a federal funding requirement? Use escrow to manage code.
X | Contract allows us to use tools, services, and hosting from vendors with a variety of pricing models, including fixed fees and variable models like “pay-for-what-you-use” services | Technology list |  | Cite Azure, report resources used. Connect to Azure material on "pay and you use" services.
N/A for POC | Contract specifies a warranty period where defects uncovered by the public are addressed by the vendor at no additional cost to the government |  | NOTE: CGI's contracts include a warranty period if identified in the customer requirements | Why N/A - use the CGI answer provided. Typical CGI warranty is 30 days?
N/A for POC | Contract includes a transition of services period and transition-out plan |  | NOTE: CGI's managed services contracts typically include transition period and transition out plan. Similarly, CGI's SI&C contracts typically include joint effort and knowledge transfer plans | Why N/A - use the CGI answer provided.
Play 6 - Assign one leader and hold that person accountable
X | A product owner has been identified | RACI | We identified one person to serve at the PM for the prototype. The PM had ultimate decision making authority - REPEAT A language | Reference Photo album with him leading discussions and on HipChat addressing questions. Underscore the teaming agreement where we cite roles and who owns direction.
X | All stakeholders agree that the product owner has the authority to assign tasks and make decisions about features and technical implementation details | Team agreement | Our RACI and team agreement clarify that the PM has responsibility and decision making authority.
X | The product owner has a product management background with technical experience to assess alternatives and weigh tradeoffs | Team list | The PM served the role of PO on this effort given the labor categories outlined in Attachment B: PQVP DS-AD Labor Category Descriptions. The PM has had several projects serving in same/similar roles.
X | The product owner has a work plan that includes budget estimates and identifies funding sources | Project Roadmap | The roadmap served as the work plan for the PM. Budgeting was handled by the PM
N/A for POC | The product owner has a strong relationship with the contracting officer
Play 7 - Bring in experienced teams
X | Member(s) of the team have experience building popular, high-traffic digital services | Team list | Team members had experience with high-traffic digital services | Summary table with experience?
X | Member(s) of the team have experience designing mobile and web applications | Team list | Team members had experience designing mobile and web applications | Summary table with experience? Mention recent CW mobile win in CO.
X | Member(s) of the team have experience using automated testing frameworks | Team list | Team members had experience with automated testing | Summary table with experience? Show CA MMIS testing experience. CGI COI on testing in VA.
X | Member(s) of the team have experience with modern development and operations (DevOps) techniques like continuous integration and continuous deployment | Team list | Team members had experience with continuous integration and deployment techniques | Summary table with experience?
X | Member(s) of the team have experience securing digital services | Team list | Team members had experience securing digital services | Summary table with experience?
Play 8 - Choose a modern technology stack
X | Choose software frameworks that are commonly used by private-sector companies creating similar services | Technology list | We employed commonly used software such as Docker, Jenkins, | Show how…add link to graph on technology
X | Whenever possible, ensure that software can be deployed on a variety of commodity hardware types |  | We tested on a variety of hardware types | There are screenshots - …what we - Nicole T. response
X | Ensure that each project has clear, understandable instructions for setting up a local development environment, and that team members can be quickly added or removed from projects | Developer onboarding checklist | We have a checklist and instructions for new developers. These instructions allowed us to have the ability to add/remove developers if needed | Gab to test
X | Consider open source software solutions at every layer of the stack | Technology list | We used commonly used open source technologies | Show full tech stack showing … 5 modern tools open tools all tools Table should also include the role each tool performs for the App.
Play 9 - Deploy in a flexible hosting environment
X | Resources are provisioned on demand |  | Azure supports this option.
X | Resources scale based on real-time user demand |  | Azure supports this option.
X | Resources are provisioned through an API |  | Azure supports this option.
X | Resources are available in multiple regions |  | Azure supports this option.
X | We only pay for resources we use |  | Azure supports this option. We monitored to pay for only the resources we needed.
X | Static assets are served through a content delivery network |  | While not applicable for this POC we have used dedicated content delivery resources on past projects
X | Application is hosted on commodity hardware | Mike will get URLs | Yes our prototype is hosted on Azure | Show how Azure does this… VM based Intel friendly
Play 10 - Automate testing and deployments
X | Create automated tests that verify all user-facing functionality | Deployment Log |  | Show how…user facing…
X | Create unit and integration tests to verify modules and components | Deployment Log |  | make sure we how unit vs. integration tests
X | Run tests automatically as part of the build process | Continuous Integration Diagram |  | Diagram + Log
X | Perform deployments automatically with deployment scripts, continuous delivery services, or similar techniques | Continuous Integration Diagram | README Techinical Approach outlines this in detail.
N/A for POC | Conduct load and performance tests at regular intervals, including before public launch | Backlog story for load testing
Play 11 - Manage security and privacy through reusable processes
X | Contact the appropriate privacy or legal officer of the department or agency to determine whether a System of Records Notice (SORN), Privacy Impact Assessment, or other review should be conducted |  | This is typical practice on CGI's engagements. We identified information to be collected in concert with the CGI Security Engineer, who acted as Privacy Officer for this proof of concept.
X | Determine, in consultation with a records officer, what data is collected and why, how it is used or shared, how it is stored and secured, and how long it is kept |  | We consulted with the who CGI Security Engineer acted as Records Officer for this POC.
X | Determine, in consultation with a privacy specialist, whether and how users are notified about how personal information is collected and used, including whether a privacy policy is needed and where it should appear, and how users will be notified in the event of a security breach |  | CGI security officer drew up a requirements for a site privacy policy. The policy is reflected in our JIRA backlog as story PQVP-18.
X | Consider whether the user should be able to access, delete, or remove their information from the service |  | As part of our policy reflected in our JIRA backlog as story PQVP-18, we considered whether users should be able to access, delete and remove their information
X | “Pre-certify” the hosting infrastructure used for the project using FedRAMP |  | CGI makes hosting recommendations based on project requirements and client security standards, and assesses the infrastructure against those standards prior to deploying the application. If FedRAMP compliance is required, we would recommend CalCloud, the Azure Government Cloud, or another comparable solution that has been FedRAMP certified or independently assessed as FedRAMP compliant.
X | Use deployment scripts to ensure configuration of production environment remains consistent and controllable |  | Azure powershell scripts in GitHub (we use powershell scripts to confirm that production environment configuration is consistent; Jenkins scripts and Docker containers to confirm that application configuration is consistent)
Play 12 - Use data to drive decisions
X | Monitor system-level resource utilization in real time | New Relic and Azure Dashboards | Tested and deployed the prototype on Microsoft’s Azure Infrastructure as a Service (IaaS) solution. We used Azure’s monitoring solution for continuous infrastructure monitoring including networking, and New Relic for continuous application performance monitoring. We used the Key Performance Indicator (KPI) data to fine- tune our infrastructure solution and our application. | Show some the Azure monitoring screens….
X | Monitor system performance in real-time (e.g. response time, latency, throughput, and error rates) | New Relic and Azure Dashboards | We used the Key Performance Indicator (KPI) data to fine- tune our infrastructure solution and our application. | Tie back to Azure monitoring screens….
X | Ensure monitoring can measure median, 95th percentile, and 98th percentile performance | New Relic and Azure Dashboards | Azure monitoring resources can be configured to monitor and alert at various resource thresholds for instance 95, 98 percent utilitzation. | Tie back to Azure monitoring screens….
X | Create automated alerts based on this monitoring | New Relic and Azure Dashboards | We configured Azure to provide automated alerts. | Tie back to Azure monitoring screens….
X | Track concurrent users in real-time, and monitor user behaviors in the aggregate to determine how well the service meets user needs |  | New Relic provides monitoring for the purposes of our POC. In addition, we have a backlog story : PQVP - 51 to expand our monitoring capabilities.
X | Publish metrics internally |  | To be provided under backlog story : PQVP - 51 to expand our monitoring capabilities.
X | Publish metrics externally |  | To be provided under backlog story : PQVP - 51 to expand our monitoring capabilities.
X | Use an experimentation tool that supports multivariate testing in production | Create a backlog story | To be provided under backlog story : XXXX
Play 13 - Default to open
X | Offer users a mechanism to report bugs and issues, and be responsive to these reports | Export of JIRA; Metrics | JIRA was the tool we used to report bugs and issues. | Show examples Show metrics including Techincal Debt tracking
X | Provide datasets to the public, in their entirety, through bulk downloads and APIs (application programming interfaces) | Link to Swagger for API inventory - Roberto can provide | Our architecture supports an API interface layer.
| Ensure that data from the service is explicitly in the public domain, and that rights are waived globally via an international public domain dedication, such as the “Creative Commons Zero” waiver |  | The data we provide is passed through from open data sources such as USGS and NOAA.
N/A for POC | Catalog data in the agency’s enterprise data inventory and add any public datasets to the agency’s public data listing |  | For the scope of this POC we believe that there is no agency data present. We would align to this goal on applicable projects
| Ensure that we maintain the rights to all data developed by third parties in a manner that is releasable and reusable at no cost to the public |  | The third party data used in our POC is passed through from open data sources such as USGS and NOAA.
X | Ensure that we maintain contractual rights to all custom software developed by third parties in a manner that is publishable and reusable at no cost |  | There is no custom third party software used on this POC. CGI's best practice is to include third party software licensing with our client agreement.
| When appropriate, create an API for third parties and internal users to interact with the service directly |  | Our architecture supports an API interface layer.
X | When appropriate, publish source code of projects or components online | GitHub | All code is published in GitHub. See section XXX of README | Document code layout
X | When appropriate, share your development process and progress publicly | JIRA | Progress is tracked through JIRA. Our evidence on our process is stored in GitHub. We have a backlog story: PQPV-53 to migrate to an open instance of JIRA. | Also w/ GitHub and the artifacts within